## Time Line
Program Timeline – Pilot SLMPD BWC Program
Activities |  | Oct. '15 | Nov. '15 | Dec. '15 | Jan. '16 | Feb. '16 | Mar. '16 | Apr. '16 | May '16 | June '16 | July '16 | Aug. '16 | Sept. '16
Advertise Positions |  | x | x | x
Interview/Fill Positions |  | x | x | x
Create RFP for Cameras |  | x | x | x
SOP/Policy Development |  | x | x | x
Project Planning |  | x | x | x
Meet w/SLPOA and CAO to get approval |  | x | x | x
Purchase /Cameras Supplies |  |  | x | x | x
Training |  | x | x | x | x | x | x | x | x | x | x | x | x
Submit Quarterly Report on Program Progress |  |  |  | x |  |  | x |  |  | x |  |  | x
Community Meetings/Presentations |  |  | x |  |  | x |  |  | x |  |  | x
Activities |  | Oct. '16 | Nov. '16 | Dec. '16 | Jan. '17 | Feb. '17 | Mar. '17 | Apr. '17 | May '17 | June '17 | July '17 | Aug. '17 | Sept. '17
Submit Quarterly Report on Program Progress |  |  |  | x |  |  | x |  |  | x
Training |  | x | x | x | x | x | x | x | x | x
Evaluate Project |  | x | [8 empty] | x | x | x
Community Meetings/Presentations |  |  | x |  |  | x |  |  | x |  |  |  | x
Submit Final Report for DOJ | [12 empty] | x