## Summary CIP (1-7) (hidden)
Dept. ID | Project # | SP Area | CIP Category | Project Title | Description | Justification | Impact | Fund Impact | Priority Tier | Elected Priority | Project Rank | Sunk Cost | Cost Total | FY23 | FY 24 | FY 25 | FY 26 | FY 27 | FY 28 | GF FY23 | General Fund | Fitness | Capital Fund | Street & Bridge (210) | MFT | TIF | Water Fund | Auto Fund | Cash | Loan | Bond | Grants | Funding Total | SP Area
PW | 1 | Infrastructure Planning and Funding | Project | USACE funded stormwater project | The Stormwater Commission will meet on 12/13/21 to select a project to receive USACE funding | The project was identified in the 2018 Stormwater Master Plan update at a top quartile project. The project advancement is expected to be recommended by the Stormwater commission. Potential projects include: 17-4, 17-3, 17-9B,17-14B Target construction cost $900,000 FY24 Federal cost Local Share $331,250 includes $200,000 FY23 - Engineering Design | The project will reduce flooding in Niles. | Project will likely result in a reduction in the amount of calls for service received. | 3 |  |  |  | 1325000 | tbd | tbd | tbd | tbd | tbd | tbd | 0 | [11 empty] | 1325000 | 1325000 | Financial Stability and Transparency
PW | 2 | Infrastructure Planning and Funding | Project | Implementation of Entrance and Roadway Signage Plan | In 2016, a comprehensive plan was developed for the installation of various signage throughout the Village, including entrance signage and roadway signage identifying Niles and wayfinding to key points within Niles. | Signage assists with branding, economic development and the overall aesthetics of Niles. | Economic development and improved aesthetics. | This is a multi-year project with varying costs each year dependent on which signage is being constructed and/or erected. These costs will be determined by which construction projects are scheduled for many of the key locations. | 1 |  |  |  | 150000 | 150000 | tbd | tbd | tbd | tbd | tbd | 150000 | 150000 | [11 empty] | 150000 | Diversified Economic Development
PD | 3 | Infrastructure Planning and Funding | Project | Police Training Room Update | Update IT equipment including: replacing existing control tower with modern control function, create "one touch" system, create wireless Bluetooth connection, create wireless microphone system to be used by instructors and presenters, capability of displaying different outputs (linking with VON cameras i.e. LPR's surveillance cameras, etc.). Lastly, replacing stained carpet and adding electrical outlets to the floor. | Currently, the PD training room IT equipment is difficult to work and only a few people in the department know how to operate the system. If these individuals are not here, other PD members are not able to utilize the control systems. When you plug in the HDMI cable to the laptop the system needs to be reset. The control plane on the wall has never worked. The PD training room hosts visitors for classes and for cake and coffee for retirement parties. The carpet is badly stained beyond cleaning capabilities and gives a negative impression of the PD when there are visitors. Additionally, when the PD replaces the carpet with new flooring, that is the ideal time to install outlets on the floor | The completion of this project will bring the NPD into the 21st century and NPD staff and instructors will be able to utilize the training room with ease. The system in place is very complicated to use and only a few staff members know how to operate the system. The carpet in the training room has been cleaned numerous times and the carpet is stained beyond cleaning capability. When the carpet is replaced, it is the best time to add electrical outlets into the floor for visitors to plug in their laptops for training. |  | 3 |  |  |  | 0 | tbd | tbd | tbd | tbd | tbd | tbd | 0 | [12 empty] | 0 | Marketing and Communication
PW | 10 | Infrastructure Planning and Funding | Project | North Branch Trail Connection - Bunker Hill | Trail Connection from the intersection of Touhy and Caldwell to the North Branch Trail $560,000 construction costs $20,000 redesign $49,600.82 Engineering expenditure to date ($30,000 grant reimbursed) | This project was originally conceived as an economic development project to direct bike traffic from the busy North Branch Trail to the Touhy Triangle. The BPAG has supported the project. | The project will increase pedestrian safety and interconnection to the North Branch Trail | Previous funding: $49,600.82 for Phs 1 and Phs 2 engineering FY23 $112,500 Local match | 1 |  |  | 49600.82 | 580000 | 580000 | [5 empty] | 112100.82 | 112100.82 | [10 empty] | 517500 | 629600.82 | Infrastructure Planning and Funding
PW | 12 | Infrastructure Planning and Funding | Project | Oakton Street and Caldwell Avenue - Multimodal improvements | Off street pedestrian and multimodal improvements on CALDWELL AVENUE (FAU 0376) & OAKTON STREET (FAU 1332) FROM VAPOR LANE TO I-94 EDENS EXPRESSWAY Morton Grove is leading this project and Niles is only responsible for cost sharing. Niles share is estimated at $260,000 total | Following resident outreach the Village of Skokie, Morton Grove, and Niles formed a partnership to pursue funding of pedestrian improvements from the intersection of Caldwell and Oakton to Niles West High school. The BPAG has been generally supportive of the project. | The project will increase pedestrian safety | Previous funding: $40,000 for Phs 1 engineering cost share FY23 $220,000 FY24TBD Schedule is dependent on IDOT | 1 |  |  | 40000 | 220000 | 220000 | tbd |  |  |  |  | 220000 | 220000 | [10 empty] | 2860400 | 3080400 | Foster Community Identity
PW | 13 | Infrastructure Planning and Funding | Project | Golf Road, Milwaukee Avenue, and Greenwood Avenue - Sidewalk Infill | The Village is in the process of designing sidewalk infill from on Golf Road from Dee Road to Washington Road, on Greenwood Avenue from Golf Road to Sunset Road, and Milwaukee Avenue from Golf Road to Maryland Street. $299,079.52 Engineering Design to date $3,400,000 Estimated construction cost, $340,000 Construction Engineer | Golf Road and Greenwood Avenue have been subject to multiple pedestrian fatalities in the past 10 years. Sidewalk is missing in multiple locations which can result in pedestrian walking in the roadway. The sidewalk infill will provide a safer and more accessible space for pedestrians on these routes. | The project will increase pedestrian safety | Previous funding: $299,079.52 for design FY 23 Budget impact: $200,000 Land Acquisition FY 24 Budget impact: $750,000 Local Match Schedule is dependent on ROW certification | 1 |  |  | 299079.52 | 950000 | 200000 | 750000 |  |  |  |  | 200000 | 950000 | [10 empty] | 4299000 | 5249000
PW | 7 | Infrastructure Planning and Funding | Project | Public Works Salt Dome & Storage Facility (Phase 2 & 3) | Public works salt dome replacement & storage facility. | The public works salt dome needs to be replaced. The current salt dome is failing. There are structural problems that cant be fixed. Along with structural concerns, the salt dome is under sized. In conjunction with the salt dome being replaced, the current storage facility is failing. Major structural repairs are needed. Both issues need to be resolved at the same time. In order for the salt dome to be rebuilt, infrastructure needs to be relocated to where the storage facility garage is located. Once completed, the new storage garage can be rebuilt. This project has gone before the Public Works Committee and a power-point presentation was given to the Mayor and Finance Committee. This project is per the Public Works Campus Master Plan completed in 2017. | A new salt dome would increase safety for staff. Loading the salt dome with a front end loader is not the safest way of pushing in salt. Vehicles have tipped over inside the salt dome on multiple occasions. The current salt dome is failing due to roof damage and concrete damage. Many of these issues are past simply repairing them. The salt dome is undersized. Clear Roads Best Management Practices states that a salt dome should hold 150% of annual usage. The salt dome only holds approximately 1800 tons of salt. Niles averages 3,871 tons per year. The new salt dome would hold approximately 6,413 tons of salt. This would allow the village to purchase salt using off season pricing. There would be a considerable price difference. Currently staff is purchasing salt at peak usage and runs the risk of not being able to acquire salt. | There will be a reduction is salt purchasing cost as staff will not need to purchase salt during peak times. Overtime will be reduced for salt deliveries. Reduction in temporary repair costs associated with failing building and salt dome. | 2 |  |  |  | 3890000 | 190000 | 2000000 | 1700000 | tbd | tbd | tbd | 0 |  |  | 3890000 | [9 empty] | 3890000
FD | 8 | Infrastructure Planning and Funding | Project | Fire Station #2 | This is a multi-phase project to replace the aging and failing fire station 2 building. This project includes feasability analysis to determine building and land needs, as well as architectural design, possible land acquisition and construction. | The existing fire station is approaching sixty years old and the building infrastructure continues to fail on a regular basis. This includes roof leaks, plumbing, electrical and structural issues. The cost of maintenance to keep the existing building functional is pushing the cost/benefit towards building replacement. In addition, the needs of the fire department have changed over the years and modernization is essential to moving forward with fire department operations, including the ability to fit modern fire apparatus in the fire station. | In addition to reducing annual building maintenance costs, a new fire station will allow the fire department to adapt to modern demands, including the space for modern fire apparatus. |  | 3 |  |  |  | 0 | tbd | tbd | tbd | tbd | tbd | tbd | 0 | [12 empty] | 0
PW | 16 | Infrastructure Planning and Funding | Project | Touhy Avenue at Gross Point Road Intersection Improvements | Intersection improvement at Touhy and Gross Point Road. The improvement include a multimodal trail, roadway widening, left turn lanes, and lighting. Construction Cost estimate: $3,400,000 | The intersection at Touhy and Gross point has a skew angle and the lack of left tuyrn lanes that make the intersection unsafe. In addition there is a lack of coherent pedestrian route on Touhy from Gross Point Road to Caldwell Avenue. | The project will increase bicycle safety with offstreet multimodal trail. The project will increase roadway safety with left turn lanes and lighting. The project will increase pedestrian safety by completing infill on Touhy Ave. | FY23 $160,000 Local Match FY23 $340,000 Phs 3 engineering (80% reimbursable) Previous expenditure: (LA Services $178,519; Phs 2 Design $223,813; Land Acquisition $1,045,000, Phs 1 Engineering $111,152) | 1 |  |  | 1558484 | 500000 | 500000 | [5 empty] | 500000 | 500000 | [10 empty] | 3200000 | 3700000
PW | 20 | Infrastructure Planning and Funding | Project | Touhy Bridge Project - Local Improvements | The Village is responsible for various non-participating costs related to the Touhy Bridge project. | Per July 2018 Letter of intent the Village made a commitment to fund the folowing project elements: Watermain relocation, emergency vehicle preemption, Private benefit traffic signal, roadway lighting, aesthetic bridge imporvements. | The project will increase bicycle safety. The aesthic improvements to the bridge have been requested by multiple elected officials | FY23-FY24 $650,000 | 1 | x |  |  | 650000 | 0 | 650000 |  |  |  |  | 0 | 650000 | [11 empty] | 650000
PW | 21 | Infrastructure Planning and Funding | Project | Caldwell Avenue Niles sign and lighting | Niles branded sign on the Caldwel Avenue Bike Bridge. Painting of Bridge, railing rework and lighting | The existing Caldwell Bike Bridge is very under stated and are not celebrated. The elected officials have requested an entrance banner sign is placed on the existing bridge. | The project will improve aesthetics to support redevelopment and beautify the Village. | There will be minor addition to electricity costs FY23 $300,000 Construction cost | 1 | x |  |  | 300000 | 300000 | [5 empty] | 300000 | 300000 | [11 empty] | 300000
PW | 22 | Infrastructure Planning and Funding | Project | Bridge Flag Poles | Installation of Flag Poles at various Chicago River Bridges in Town. Including: Howard Street, Touhy Avenue, and Hart Road | The existing Chicago River Bridges in town are very under stated and are not celebrated. The elected officials have requested flag poles are placed at the approaches to the bridges. | The project will improve aesthetics to support redevelopment in the area. The project will celebrate the bridges and create a community identifier for Niles | FY23 - $40,000 FY24 - $80,000 There will be minor addition electricity costs as well flag replacement and manpower for operating the poles | 1 | x |  |  | 120000 | 40000 | 80000 |  |  |  |  | 40000 | 120000 | [11 empty] | 120000
PW | 25 | Infrastructure Planning and Funding | Project | Pavement Rehabilitation Senior Center (many times delayed - seven years) | Rehabilitation of the Senior Center Parking Lot | The senior center parking lot is at the end of its useful life and needs major maintenance and rehabilitation. The Senior Center Parking lot is also the venue for various Civic events such as the Holly Jolly festival. The deterioration of the lot has also resulted in workers compensation claims. | The project will improve aesthetics to support economic development and beautify the Village. | The lot should be resurfaced on an approximately 15 year schedule. The 2021 estimated cost for this work is $200,000 | 1 |  |  |  | 200000 | 200000 | [5 empty] | 200000 | 200000 | [11 empty] | 200000
PW | 26 | Infrastructure Planning and Funding | Project | Touhy Avenue Gap Lighting Franks Ave to Milwaukee Ave. (combine with proj 16) | The Gross Point and Touhy Intersection improvement includes new lighting up to the Chicago River Bridge. This project provides lighting for the gap between Franks and Milwaukee | As part of either the Touhy Bridge replacement or the intersection improvement, IDOT will require ComEd to take take down the existing Touhy Avenue Street lighting since it does meet current design standards. This project will allow for uniform corridor lighting from Milwaukee Avenue to Caldwell | The project will improve aesthetics to support redevelopment and beautify the Village. The project maintains and improves the current level service. | There will be minor addition to electricity costs FY23 $160,000 Design and Construction cost | 1 |  |  |  | 160000 | 160000 | [5 empty] | 160000 | 160000 | [11 empty] | 160000
PW | 15 | Infrastructure Planning and Funding | Project | Pedestrian Safety Improvements at Caldwell and Cleveland; Wauekgan and Cleveland | The Village is in the process of designing pedestrian crossing improvements at the above intersections. $85,486.66 Engineering Expenditure to date $250,000 Estimated cost for final design and construction engineering $1,900,000 estimate for construction | The Amling memorial trail follows Cleveland Street where it crosses Waukgan Road and Caldwell Ave. The intersections have long been slated for pedestrian safety improvements. More recently the BPAG has recommended improvements are installed and has been involved in the design development process. | The project will increase pedestrian and bicycle safety; check on MFT fund balance; | Previous funding: $85,486.66 for design; project cost increase to $2,000,000 FY 23 budget impact $750,000-$1,500,000 Schedule is dependent on IDOT review. Federal funding eligible but that increases the project timeline 3-4 years | 2 |  |  | 85486.66 | 2000000 | 1000000 | 1000000 | tbd | tbd | tbd | tbd | 0 |  |  |  |  | 2000000 | [7 empty] | 2000000
PW | 32 | Infrastructure Planning and Funding | Project | Village Hall Entrace | Streetscape improvements at Milwaukee and Waukegan; and Oakton and Waukegan | The failing infrastructure, outdated aesthetics and lack of civic building pride is in need of a complete face-lift. |  | Project needs more details to develop funding plan | 1 | x |  |  | 3000000 | 250000 | 2750000 | tbd | tbd | tbd | tbd | 250000 | 3000000 | [10 empty] | 1800000 | 4800000
PW | 39 | Infrastructure Planning and Funding | Maintenance | Fire hydrant flushing and testing program | Flush and test all Village fire hydrants. | Fire hydrant testing is very important to the Village of Niles. Hydrants should be tested and inspected at least annually. Hydrant maintenance and upkeep is one of many steps to keeping the Village's Insurance Service Office (ISO) certification low. ISO developed ratings for fire departments and municipalities. The ratings calculate how well equipped fire departments are to put out fires in that community. The ISO provides this score to homeowners insurance companies, which helps determines homeowner’s insurance rates. A higher ISO score results in lower insurance rates. | Find fire hydrants that are inoperable during the annual testing and repair or replace them. A higher ISO score for the Village. | Provides necessary information of the Village’s distribution system and increases the safety of the residents and businesses in Niles. | 1 |  |  |  | 354000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 354000 | [11 empty] | 354000
PW | 18 | Infrastructure Planning and Funding | Project | Lead Service Line Replacement | Complete replacement of lead services lines which require emergency repair | HB-3739 created a statutory requirement for the Village to completely replace lead service lines when they are disturbed. Partial replacement of lead service lines present a public health issue. The Village is working on a lead service line replacement plan which must be completed by 2024. However as an interim policy the lead services that are disturbed after January 1, 2022 must be replaced in full. The Public Works committee will consider this issue on 12/17/21 | The project will eliminate a public health hazard in Niles and improve the marketability of our housing stock. | The annual cost to our water fund will be in the range of $500,000 to $600,000 depending on how many repairs are required each year. FY23 $600,000, FY24 $600,000, FY25$600,000, FY26 $600,000, FY27 $600,000 | 1 |  |  |  | 3600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | [6 empty] | 3600000 | [5 empty] | 3600000
PW | 51 | Infrastructure Planning and Funding | Project | Greenleaf Sewer Rehabilitation | Sanitary sewer repair and lining for Greenleaf sewer in Chesterfield Gardens | The project was identified through the Public Works televising program as a sewer in need of major maintenance and repair. | The project will reduce sewer backups in Chesterfield Gardens. | Project will result in a reduction in the amount of calls for service for sewer cleaning to the Chesterfield Gardens. FY23 $167,000 Construction and construction engineering cost Previous costs: $21,436 Engineering Design | 1 |  |  | 21436 | 167000 | 167000 | [5 empty] | 167000 | 188436 | [11 empty] | 188436
PW | 56 | Infrastructure Planning and Funding | Maintenance | Replacement of Exterior Door and Frames at 1000 Civic Center Drive | Demolition and replacement of 12 exterior doors and framework 1000 Civic Center Drive | The exterior doors and framework are badly corroded, potentially unsecure, and have past their life expectancy. | Increased security, improved aesthetic, improved envelope protection from weather. |  | 1 |  |  |  | 108000 | 108000 | [5 empty] | 108000 | 108000 | [11 empty] | 108000
|  |  |  | Village Hall Interior Lobby Redesign |  |  |  |  | 1 |  |  |  | 20000 | 20000 | [5 empty] | 20000 | 20000
PD | 5 | Infrastructure Planning and Funding | Project | Niles Law Enforcement Memorial | The statue titled “The Protector”, will feature a police officer standing atop a pedestal saluting. An officer’s salute exhibits a long standing gesture of friendship, confidence and professionalism which is intended to honor all police officers killed in the line of duty, especially Niles Police Officer Steven Zourkas who was killed in the line of duty in 2005. | This display shall pay tribute to every police officer serving communities throughout the country and shall serve as a visual reminder of the commitment by the Village of Niles to remember the fallen. The Committee is working hard to effectuate the Village’s unwavering support for all members of law enforcement. | The Niles Law Enforcement Memorial statue is being built to pay tribute to police officers that have made the ultimate sacrifice for the communities they serve, and to honor police officers that put their lives on the line everyday protecting the communities they are sworn to serve. This is of special significance to the Niles Police Department having lost Officer Steven Zourkas in the line of duty in 2005. | Total project cost: $95,000.00. Public Works will be covering demolition, excavation and hauling of debris, electrical work, site utilities landscaping and some concrete work, which will cost approximately $20,000.00-$35,000.00. Anything beyond $35,000.00, will be paid for through donations by the Niles Law Enforcement Memorial Committee. | 2 |  |  |  | 35000 | 35000 | [5 empty] | 35000 | 35000 | [11 empty] | 35000
PD | 6 | Infrastructure Planning and Funding | Project | Automated License Plate Reader program | This project involves the purchase of 12 Automated License Plate reading cameras as well as updating our 2 current license plate reading cameras. The price includes all hardware and software as well as installation. The system will also allow our Axon squad car cameras to function as mobile License plate readers. | License plate reading cameras (LPR) are an essential tool in fighting crime and protecting both our residents and businesses. The LPR system will provide the Niles Police Department with analytics and access to billions of license plate scans from our LPR cameras as well as cameras that are deployed in cities throughout the country. The information provided by the LPR cameras will be invaluable for all types fo crimes that occur within the Village of Niles. For example, an armed robbery occurs and the offender flees in a vehicle. A witness of victim and provide a vehicle description and a partial license plate. That information can be entered and investigators would have instant access to images of vehicles matching the description. | This project will provide the following benefits:Assist in locating carjacked vehicles and increase the likelihood of locating offenders. LPR cameras will assist in combating drug trafficking "hot spots" within the village by using convoy analysis. LPR's will help to combat and disrupt catalytic converter and vehicle thefts by using associate analysis and identifying vehicles that frequently travel together. The LPR system will assist in locating suspects that fell by using the comprehensive plate location analysis as well as the use of predictive analytics and historical vehicle location data. Burglary investigations will benefit from the use of common license plate analysis to generate a suspect via previously observed vehicles in areas of recent burglaries. LPR cameras will placed in corridors that have statistically high numbers of DUI's providing increased assistance in our DUI enforcement. | This purchase will have an initial impact of $38,896.00 and a recurring impact of $34,396.00. | 2 |  |  |  | 210876 | 38896 | 34396 | 34396 | 34396 | 34396 | 34396 | 38896 | 210876 | [11 empty] | 210876
PW | 23 | Infrastructure Planning and Funding | Project | Lawrencewood Gardens and Oasis Neighborhood Storm Sewer Improvement | Storm sewer Improvement from Mulford and Octavia to Howard Street Storm sewer outfall | The project was identified in the 2018 Stormwater Master Plan update at a top quartile project. Stormwater Project # 17-7a The project advancement was recommended by the Stormwater commission. The high cost of this project requires the establishment of a stormwater utility. Schedule is dependent on grant funding or other revenue source. Project should be projected for FY28 due to the size and scope. | The project will reduce flooding in the Lawerencewood Gardens and Oasis Neighborhoods The project is an extension of the Howard Street Outfall | Project will likely result in a reduction in the amount of calls for service received from the Lawerencewood Gardens and Oasis Neighborhood; potential SSA funding | 3 |  |  |  | 10400000 | [5 empty] | 10400000 | 0 | [6 empty] | 10400000 |  |  |  |  | 2000000 | 12400000
PW | 24 | Infrastructure Planning and Funding | Project | Oketo Avenue Stormwater Improvement | Oketo Avenue Storm sewer replacement from Monroe Street to Keeney Street | The project was identified in the 2018 Stormwater Master Plan update at a top quartile project. Stormwater Project # 17-26P The project advancement was recommended by the Stormwater commission | The project will reduce flooding on Oketo Avenue. The project is an extension of the Cleveland Sewer | Project will likely result in a reduction in the amount of calls for service on Oketo Avenue; Grant dependent project FY24 $650,000 Construction cost Previous costs: $55,050 Engineering Design | 2 |  |  | 55050 | 650000 |  | 650000 |  |  |  |  | 0 | [6 empty] | 405050 |  |  |  |  | 300000 | 705050
PW | 11 | Infrastructure Planning and Funding | Project | Oakton Street Pedestrian network connections | Pedestrian network connections from the Chesterfield Gardens neighborhood to the newly pedestrian improved intersection of Caldwell and Oakton | The BPAG has supported the project and is expected to be included in the recommended projects as a result of the bike and pedestrian plan update. | The project will increase pedestrian safety and interconnection to the Oakton Street mulitmodal trail | FY23 $30,000 Design Engineering Fy24 $ 170,000 Construction | 2 |  |  |  | 200000 | 30000 | 170000 |  |  |  |  | 30000 | 200000 | [11 empty] | 200000
PW | 17 | Infrastructure Planning and Funding | Project | Shermer Road - Rehabilitation and Multimodal Improvements | Rehabilitation of Shermer Road from Waukegan north to Village Limit. Project includes on-street bike and improvements per 2014 Bike and ped plan | 2018 State of the Streets report indicates Shermer is due for rehabilitation Project includes on-street bike and improvements per 2014 Bike and ped plan | The project will increase bicycle safety and pavement is at the end of its useful life | FY23 $180,000 Phs 1 engineering Fy 24 $180,000 Phs 2 engineering FY26-27 $360,000 Local match | 2 |  |  |  | 1080000 | 180000 | 180000 |  | 360000 | 360000 |  | 180000 | 900000 |  |  |  | 180000 | [7 empty] | 1080000
PW | 27 | Infrastructure Planning and Funding | Project | FY26-27 Street Improvement Program | Pavement Rehabilitation Project | The streets are as identified in the 2018 State of the Street Report. The State of the streets report will be updated prior to FY26 and the recommended funding level will be adjusted at that time. | The $2,700,000 annual funding rate is expected to be sufficient to maintain our average PCI after the larger bond project. This dollar value is based on the 2018 state of the street report. The State of the streets report will be updated prior to FY26 and the recommended funding level will be adjusted at that time. | $2,700,000 year | 1 |  |  |  | 9000000 |  |  |  | 3000000 | 3000000 | 3000000 | 0 |  |  |  | 4500000 | 4500000 | [7 empty] | 9000000
PW | 28 | Infrastructure Planning and Funding | Project | FY23-25 Street Improvement Program | Pavement Rehabilitation Project | The streets are as identified in the 2018 State of the Street Report. | The Goal is to achieve an average Village Pavement Condition Index rating of 65. The expenditure of these funds will save many streets from more costly future maintenance and rehabilitation | Debt service payments to be calculated by Finance | 1 |  |  |  | 18700000 | 4600000 | 7050000 | 7050000 | tbd | tbd | tbd | 0 | [10 empty] | 14800000 | 3900000 | 18700000
PW | 29 | Infrastructure Planning and Funding | Project | Touhy Avenue Banner sign and monuments | Niles branded sign across Touhy Avenue at the Chicago River. Decorative Monument lights at Touhy Avenue Bridge. | The existing Chicago River Bridges in town are very under stated and are not celebrated. The elected officials have requested a banner sign and monument piers (similar to Howard for the Touhy Bridge approaches) | The project will improve aesthetics to support redevelopment and beautify the Village. | There will be minor addition electricity costs FY24 $300,000 Construction cost | 2 | x |  |  | 300000 | 0 | 300000 |  |  |  |  | 0 | 300000 | [11 empty] | 300000
PW | 30 | Infrastructure Planning and Funding | Project | Milwaukee Avenue Streetscape Phase V | Streetscape improvements from Monroe to Greenwood | The Milwaukee Corridor committee recommended the proposed design as part of their normal agenda process. The schedule is dependent on receiving ITEP funds. | The project will improve aesthetics to support redevelopment and beautify the Village. | There will be added maintenance costs for landscape brick pavers, street furniture, pedestrian lights, and irrigation systems; grant dependent Project funding ratio is 80% federal/20% local | 3 |  |  |  | 4500000 | tbd | tbd | tbd | tbd | tbd | tbd | 0 | [8 empty] | 900000 |  |  | 3600000 | 4500000
PW | 31 | Infrastructure Planning and Funding | Project | Milwaukee Avenue Streetscape Phase VII | Streetscape improvements at Milwaukee and Waukegan; and Oakton and Waukegan | The Milwaukee Corridor committee recommended the proposed design as part of their normal agenda process. The schedule is dependent on receiving ITEP funds. | The project will improve aesthetics to support redevelopment and beautify the Village. | There will be added maintenance costs for landscape brick pavers, street furniture, pedestrian lights, and irrigation systems; grant dependent Project funding ratio is 80% federal/20% local | 3 |  |  |  | 1250000 | tbd | tbd | tbd | tbd | tbd | tbd | 0 | [8 empty] | 250000 |  |  | 1000000 | 1250000
PW | 41 | Infrastructure Planning and Funding | Maintenance | Crack Sealing | Crack sealing roads to prevent water infiltration. | This work extends the life of the asphalt by preventing water from entering cracks, freezing and damaging the asphalt when it expands. | Crack sealing extends the life of recently paved roadways. The life of your asphalt hinges on asphalt maintenance, so getting an asphalt sealing to combat the cracks is crucial. Asphalt surfaces are compromised by cold weather, extended exposure to UV rays, rain and other elements: asphalt pavement can become brittle and bleached of essential oils over time and begin to crack. When a crack opens up, it is absolutely critical to close it with crack sealants to prevent water from leeching in below the pavement surface. Water is your worst enemy, because it freezes, expands, then thaws and repeats, exacting a toll on your sub base and exponentially worsening existing damage. | Reduction in damage to roadways. With proper maintenance the roads will be safer for pedestrians and vehicular traffic. Life of roads will be extended lessoning the cost of street replacement. | 2 |  |  |  | 900000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 900000 | [11 empty] | 900000
PW | 33 | Infrastructure Planning and Funding | IT/Purchase | Above Ground Mobile Truck Lifts | (6) Mobile Column Lifts are required to safely lift a wide range of heavy duty vehicles quickly and efficiently. From water sewer vans and pumper trucks to PACE buses and Tower trucks, these mobiles lifts can safely handle them all. Lifting capacities of 18,500lbs. per column can handle any vehicle that the Village owns | Our existing lifts are obsolete and cannot safely lift modern heavy duty vehicles. | Decreased potential workman's compensation claims by keeping staff off of their backs and safely elevating the trucks to a proper working height. This is also a far cheaper alternative with less environmental impact than replacing with in-ground hydraulic truck lifts |  | 2 |  |  |  | 80000 | 80000 | [5 empty] | 0 | [7 empty] | 80000 |  |  |  |  | 80000
FC | 34 | Infrastructure Planning and Funding | Maintenance | Replacement of Front Lobby Doors Interior and Exterior | The Front Lobby doors of Fitness Center interior/exterior will be replaced. Type of replacement will be considered by evaluation/quoted fee from vendor | The Front Lobby doors are original to the building and have reached their life expectancy. They are both a safety and an environmental concern. The front area of the fitness center creates a wind tunnel and during extreme weather conditions the both exterior/interior does do not shut properly. People entering/existing the building are not able to open the doors properly creating a potential for injury. In addiction due to these doors not closing properly the controlling the heating and cooling of this area is extremely difficult. | Replacement of Front Lobby Doors will address both the safety and environmental concerns of the lobby area. The planning/timing of this project will need to take place during the warmer months. Involvement of IT and PW will need to take place in assisting of security and possibility of re-locating entering/exiting of facility as this is the fitness center's main entrance. | The Front Lobby Doors will be under a warranty for a period of time. therefore service calls to vendors and calls into PW for assistance will be greatly reduced. IT will need be involved in the beginning of this project to make sure that the replacement doors will work within the existing fitness center security system which involves the scheduling of opening/closing the building entrances/exits | 2 |  |  |  | 0 | tbd | tbd | tbd | tbd | tbd | tbd | 0 |  | 0 | [10 empty] | 0
FC | 35 | Infrastructure Planning and Funding | Maintenance | Replacement of Flooring in Cardio/Weight Area of the Fitness Center | The carpet and mondo flooring in Cardio/Weight Area of the Fitness Center will be replaced Type of flooring replacement and configuration will be considered by vendor's evaluation/quoted fee | Cardio/Weight Area flooring is original and has experienced an extreme amount of wear and tear. This includes not only foot traffic but of bodily fluids from sweating. We are limited to how much cleaning of the carpet can be done without creating more wear and tear to this area. In addition we are seeing a need for less carpet and more mondo flooring to expand the weight area (member requests) and ease of keeping clean | Replacement and reconfiguration of the carpet/mondo flooring will allow for expansion of the weight area. This is a request from not only our current membership base but the future of fitness workout. We believe this re-configuration of the fitness room will attract a younger membership base. While we acknowledge increasing the weight area will decrease the cardio area, this will allow fitness staff to evaluate the use of cardio equipment, such as not repairing equipment (expense) that is end of life and not being used by members (waste of floor space) | Previous expenses : In-house such as cleaning and minor repairs to the carpet area. Professionally cleaned yearly $250.00 This project will reflect a positive impact on entering the Cardio/Weight Area and allow for a better work out configuration for new and existing members. | 2 |  |  |  | 0 | tbd | tbd | tbd | tbd | tbd | tbd | 0 |  | 0 | [10 empty] | 0
FC | 36 | Infrastructure Planning and Funding | Maintenance | Re-Support of Pool Duct Work To Beams | Labor, materials,and lift needed to install additional trapeze for all duct work hanging over pool area (Please see additional quote information attached to the profile) | On May 26, 2021 staff from the Niles Family Fitness Center (NFFC), Public Works (PW), Community Development (CD) and the Acting Village Manager walked through the NFFC facility. This exercise was conducted in reaction to a failure of a lighting fixture above the NFFC pool in February 2021. 1. Concerns were raised that the HVAC above the pool was corroding and risked potentially falling. During the annual August pool draining, NFFC staff should have a company secure HVAC above the pool. (This was discussed and place on hold until the FY 23 Budget) | This project was placed on hold until it could be placed in the FY 23 Budget under capital improvements. It would be completed as a safety enhancement to the pool area. | It would be a one time expense. This is a non-revenue producing project(please see attached quote for expenses) | 2 |  |  |  | 21980 | 21980 | [5 empty] | 0 |  | 21980 | [10 empty] | 21980
FC | 37 | Infrastructure Planning and Funding | Maintenance | Fitness Center HVAC Gym Roof Top Units (RTU) | Replacement of two existing Gym HVAC RTU | These are the last two original units to be replaced. They are currently over 20 years old and have met their life expectancy Currently the fitness center has no back up Gym HVAC RTUs that can be used during extreme weather conditions where temperatures fluctuate or in the case of RTU failure. The gymnasium is a multi use fitness area that requires quality air circulation and temperature control | With the addition of (2) HVAC gym roof top units the Fitness Center will have a fully functioning HVAC system. This will allow those members and guests utilizing the gymnasium, track, open basketball, and group fitness classes to work out in well circulated temperature controlled environment | In 2020 (2) HVAC Roof Tops units were replaced for a cost of $120,000 funded by CIP. These two Gym RTUs are under warranty until 2025 and have incurred no maintenance costs Annual estimated maintenance expenses for the remaining two gym roof top units for this year has been approximately $5,000 Their will be no maintenance expenses with new RTUs as they will be under a five year warranty | 2 |  |  |  | 120000 | 120000 | [5 empty] | 0 |  | 120000 | [10 empty] | 120000
FC | 38 | Infrastructure Planning and Funding | Maintenance | Membership Service Desk (Front Desk)-Remodel | The Membership Service Desk (Front Desk) will be remodeled Type of remodeling will be considered by vendor evaluation/quoted fee | The Membership Service Desk (Front Desk) is original to the building and has experienced wear and tear as this is the focal point of all business conducted by the fitness center (please see pictures attached). If the Front Lobby Door Replacement were to be approved this would be an optimal time to upgrade the Membership Service Desk (Front Desk). | Remodeling of the Membership Service Desk(Front Desk) area will give an aesthetically pleasing visual as people enter and exist the Fitness Center. This area is not only used by Fitness Center's members and guests but is also used by people making there way to and from the Senior Center and Family Services. In future planning discussions it has been suggested that the Fitness Center Lounge Area host the Arts Council Special Events. If that were to take place the main lobby of the Fitness Center would need to be visually appealing to all those entering. As we are all aware first impressions are lasting impressions. Involvement of IT/PW will need to take place in assisting of moving of computers and the possibility of re-locating the Membership Service Desk (Front Desk) | Previous expenses we done in-house and were general and minor repairs to shelving an cabinetry. This project will not be revenue producing and expenses are minor. The project will reflect a positive impact on entering the Fitness Center as well as other areas of the building | 2 |  |  |  | 0 | tbd | tbd | tbd | tbd | tbd | tbd | 0 |  | 0 | [10 empty] | 0
PW | 43 | Infrastructure Planning and Funding | Maintenance | Tree Planting | Planting trees along village parkways and properties. | The Village of Niles is a Tree City USA. Tree City USA status in critical for funding and grant applications. | Trees combat climate change, help reduce storm water runoff, prevent soil erosion, tree reduce violence, produce economic opportunities, add protection for pedestrians from vehicular traffic. | Trees require maintenance. In order to invent in the growth of Niles and green infrastructure Niles will need to commit funding to maintain village trees. | 2 |  |  |  | 330000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 330000 | [11 empty] | 330000
FD | 40 | Infrastructure Planning and Funding | Maintenance | Concrete Driveway Repair | The existing concrete driveway at Fire Station 2 is failing where the fire apparatus regularly drive through. This includes the front entrance to the fire station. | This is both a cosmetic and a safety concern. Visitors to the fire station regularly trip over the holes and gaps created by the failing concrete. In addition, the driveway needs to safely hold the weight of the fire apparatus as they return to quarters. The Tower Ladder needs stable ground to support the outriggers during daily and weekly aerial checks and an unstable driveway poses a safety risk for operations. | Replacing specific failing sections of the concrete driveway will improve safety for fire station 2. It will maintain a safe surface for fire apparatus to drive on, while returning to quarters. It will also eliminate the tripping hazards that currently exist for visitors to the fire station. |  | 2 |  |  |  | 0 | tbd | tbd | tbd | tbd | tbd | tbd | 0 | 0 | [11 empty] | 0
PW | 44 | Infrastructure Planning and Funding | Maintenance | Minor Asphalt Repairs | Repairs of large section of roadways. | This work is done in areas where asphalt repairs are needed, but resurfacing is not scheduled within the next five years. Locations are determined on an as needed basis. | The village benefits from this maintenance because it can delay street resurfacing until the entire street needs it. Some repairs are to great for simply filling pot holes. A large section can be completed for a better cleaner looking repair. | With proper maintenance the roads will be safer for pedestrians and vehicular traffic. Life of roads will be extended and delay street replacement. Reduction in overtime for filling potholes. Reduction in injuries to pedestrians from stepping in cracked and broken roadways. | 2 |  |  |  | 480000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 480000 | [11 empty] | 480000
PW | 42 | Infrastructure Planning and Funding | Maintenance | Pump Replacement: #2 and Pump # 4; add VFD's. | Replacement of Pump #2 and installation of a new VFD on pump #4 at the Touhy Avenue Pump Station. | Pump #2 and Pump #4 has reached its life expectancy and is recommended for replacement. In addition, variable frequency drives (VFD) will be installed to Pump #2 and #4. This will provide substantial energy savings and reduce wear and tear to the motor and pumps. This a recommendation from the Water master plan. | The biggest benefit in replacement of the motors and pumps and installing VFD's is energy cost. VFD’s are used for adjusting flow and pressure to actual demand. It controls the frequency of the electrical power supplied to a pump, thus saving significant power energy. By replacing these pumps and motors, a reduction in electrical usage of approximately 4 percent for each pump could be seen. | The previous funding for replacement of motors and pumps and installing VFD's was $180,000. Staff is anticipating a thirty-percent increase for materials. Future Funding: Staff plans on replacing three more pumps and motor and install VFD's within the next two years. The estimated cost for this is $350,000. | 2 |  |  |  | 234000 | 234000 | [5 empty] | 0 | [6 empty] | 234000 | [5 empty] | 234000
PW | 45 | Infrastructure Planning and Funding | Maintenance | Traffic Signal Maintenance | Traffic signal maintenance of intersection in the Village of Niles. | The village is required to make sure village owned traffic signals are maintained. This is completed sole source / contract with Meade. | Making sure our traffic signals are working property helps to insure even traffic flow and helps to keep drivers and pedestrians safe while traveling. | Reduction in accident claims. | 2 |  |  |  | 322731.36 | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 322731.36 | [11 empty] | 322731.36
PW | 46 | Infrastructure Planning and Funding | Maintenance | Tree Trimming | Tree Trimming along village owned parkways and properties. | The Village of Niles is a Tree City USA and allocates money for tree trimming. Tree trimming is critical for the growth of trees and for safety. Trees on the Village of Niles are separated in to five trim zones. One trim zone is completed each year. | Proper trimming improves tree health by eliminating dead or dying branches, trimming improves the overall appearance and structure of the tree, which prevents the development of broad or weak branches. It also keeps limbs from growing with weak crotches, or even crossing each other and competing for space in the crown. Tree trimming also helps to reduce storm damage. | Trees require maintenance and trimming reducing call outs for storm damage, hangers, damage to property and most of all reduces the danger to life. | 2 |  |  |  | 510000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 510000 | [11 empty] | 510000
PW | 47 | Infrastructure Planning and Funding | Maintenance | Tree Removal | Tree Removal along village owned parkways and properties. | The removal of trees that are dead, diseased or dangerous is necessary to safeguard the lives of Niles residents. It can be equally important to remove trees with diseases to stop the potential spread. | Removing trees that are dead, diseased or dangerous is necessary to safeguard the lives of Niles residents. Removal of trees that can posses hazards lowers claims of injuries and property damage. Trees that fail can cause power outages which impacts residents who survival depends on electricity. | Removal of these trees reduces call outs for storm damage, hangers, damage to property and most of all reduces the danger to life. Insurance claims are lower and phone calls to the department for service are reduced. | 2 |  |  |  | 510000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 510000 | [11 empty] | 510000
PW | 50 | Infrastructure Planning and Funding | Maintenance | Water main Valve Exercising Program | To ensure that water valves can be located efficiently and closed to isolate part of the water system in case of an emergency, water main breaks or repair. | This program verifies that the valves are in the correct operating position so as to maximize flow and pressure for firefighting and normal operation. The American Water Works Association (AWWA) recommends that each valve should be operated yearly. | Valve exercising is designed to prevent buildup/scaling on the inside of the valve which could cause the valve to be inoperable. This is done multiple times until the valve opens and closes smoothly. After the valve is exercised, the contractor documents the location of the valve, condition and if any maintenance is needed. | Repair inoperable valves when found to ensure the water system is working properly. | 2 |  |  |  | 492000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 492000 | [11 empty] | 492000
PW | 53 | Infrastructure Planning and Funding | Maintenance | Milwaukee Brick Crosswalk Replacement | Replacement of Decorative Milwaukee Crosswalks with Thermoplastic Crosswalks | The Milwaukee Corridor committee selected decorative Thermoplastic Crosswalks for the replacement of the poor performing Brick paver crosswalks. The cross walks have been replaced incrementally on an annual basis. | The project will improve aesthetics to support redevelopment in the area. The existing crosswalks are also settling and deteriorating resulting in a driving hazard. The hazard will be removed. | The cross walks will need to be replaced every 10-years or so. Replacement costs will be much less than the initial cost since much of the initial cost is related to removal of the brick paver walk. FY23 $250,000; FY 24 $25,000 design; FY 25 $250,000, FY26 $25,000 design, FY27 $250,000 | 2 |  |  |  | 800000 | 250000 | 25000 | 250000 | 25000 | 250000 |  | 250000 | 800000 | [11 empty] | 800000
PW | 48 | Infrastructure Planning and Funding | Maintenance | Sewer Cleaning and Televising Program | The sewer cleaning and televising program is to clean debris from both sanitary and storm lines and find deficiencies. | The purpose of this work is to clean debris from both sanitary and storm lines. After cleaning, internal closed circuit television is used to inspect sewers and identify structural defects, misalignments, service lateral connections and deficiencies. | The sewer cleaning and televising program provides necessary information related to the Village’s sewer system and provides better operation of the sewer system. | Identify the scope of the repairs necessary, including sewer lining, spot repairs or complete pipe section excavation and replacement. | 2 |  |  |  | 510000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 0 | [6 empty] | 510000 | [5 empty] | 510000
PW | 49 | Infrastructure Planning and Funding | Maintenance | Sewer Lining Program | CIPP is designed to restore our sewer lines to proper operating conditions. | Cured-in-place pipe (CIPP) is a trenchless rehabilitation method used to repair existing sewer pipes. CIPP is a jointless, seamless, pipe-within-a-pipe with the capability to rehabilitate sewer pipes and restore structural integrity. | One of the greatest benefits of sewer lining is there is no road construction and minimal disturbance to our residents. There is also a fifty-year design life, the same as that of a new pipe. | CIPP sewer lines that are deteriorating. | 2 |  |  |  | 1500000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 0 | [6 empty] | 1500000 | [5 empty] | 1500000
PW | 54 | Infrastructure Planning and Funding | Project | Village Hall Parking Garage Security and Thermal Intrusion Upgrade | Replace the chain roll up garage doors and man door with solid aluminum doors. Add removable thermal glass panes over the steel mesh steel windows, and piping insulation; potential inclusion with Village Hall Entrance Reconstruction | Replacing the mesh roll up garage doors and adding thermal glass panes to the underground parking garage will reduce cold/hot weather intrusion, increase security, eliminate bird traffic, and improve the garage aesthetic my increasing cleanliness. | Reducing thermal intrusion and lowering carbon footprint by reducing HVAC necessity |  | 2 |  |  |  | 150000 | 150000 | [5 empty] | 150000 | 150000 | [11 empty] | 150000
PW | 55 | Infrastructure Planning and Funding | Maintenance | Lower Level Mechanical Roof, Chiller and Access Door | Replacement of the Lower Level Mechanical Roof, Chiller Unit and Access Door at Village Hall | The Lower Level Mechanical Roof has surpassed its 25 year life expectancy and is in need of full replacement. This area was not address when the roof was previously refurbished and has failed. Failure to replace the roofing system will result in damages caused by water intrusion and will continue to the damage the infrastructure prematurely. Furthermore, the Chiller unit located on the mechanical roof is original to the building, nearly obsolete, and should be replaced at the time of removal | Best practice roofing management will extend the life of the building and eliminate water intrusion |  | 2 |  |  |  | 270000 | 270000 | [5 empty] | 270000 | 270000 | [11 empty] | 270000
PW | 52 | Infrastructure Planning and Funding | Project | Melvina Street Rehabilitation | Pavement Rehabilitation Project from Touhy to Gross Point. Watermain replacement, lighting, and bike improvements. FY 24 project | The street is identified as needing repair in the 2018 State of the Streets Report. The Water system master plan identifies the watermain as a high priority for replacement. | The project will increase fire flows to support redevelopment in the area. A revitalized Melvina Avenue will also help encourage redevelopment within the Triangle. Replacing the roadway before the PCI gets too low will reduce the scope of work and cost. | $0 - This is TIF funded so operation should not be affected Previous expenditure ($297,810 Design Engineering) | 1 |  |  | 297810 | 2600000 |  | 2600000 |  |  |  |  | 0 | [5 empty] | 2897810 | [6 empty] | 2897810
PW | 57 | Infrastructure Planning and Funding | Maintenance | HVAC Replacements at 1000 Civic Center Drive. | Replace Liebert units in server room and server room ceiling with modern equipment that is designed to handle additional IT infrastructure. | The aforementioned HVAC units have surpassed their life expectancy or are entirely obsolete and require replacement. | Being that the project is multi-tiered, workload permitting, Facilities staff can be utilized to reduce costs by purchasing individual units and installing in-house |  | 2 |  |  |  | 80000 | 80000 | [5 empty] | 80000 | 80000 | [11 empty] | 80000
PW | 58 | Infrastructure Planning and Funding | Maintenance | HVAC Replacements at PW Campus | Replacements of Above ceiling Computer Room Unit remote condenser serving Server Rooms | The aforementioned HVAC units have surpassed their life expectancy or are entirely obsolete and require replacement. | Being that the project is multi-tiered, workload permitting, Facilities staff can be utilized to reduce costs by purchasing individual units and installing in-house |  | 2 |  |  |  | 50000 | 50000 | [5 empty] | 50000 | 50000 | [11 empty] | 50000
PW | 59 | Infrastructure Planning and Funding | Maintenance | HVAC Replacements at 7000 W. Touhy | Rooftop Unit RTU-1 serving Jail Cells,Rooftop Unit RTU-3 serving Lower Level Locker Rooms,Rooftop Unit, Rooftop Unit RTU-6 serving the Second Floor Offices, Add Mini-Split System to Fingerprint Area,Computer Room Unit CRIU-3 ducted cooling unit and remote condenser serving Lower Level Electrical Room | The aforementioned HVAC units have surpassed their life expectancy or are entirely obsolete and require replacement. | Being that the project is multi-tiered, workload permitting, Facilities staff can be utilized to reduce costs by purchasing individual units and installing in-house |  | 2 |  |  |  | 300000 | 300000 | [5 empty] | 300000 | 300000 | [11 empty] | 300000
PW | 60 | Infrastructure Planning and Funding | Maintenance | HVAC Replacements Shared Units for Senior Center and Family Services | Hot Water Pumps serving entire building AHU-1 serving Senior Center & Family Services AHU-1 Variable Frequency Drives serving Senior Center & Family Services Wood gas piping supports on roof are deteriorated. Trane Temperature Controls serving building are obsolete | Multiple components of the HVAC system at 999 Civic Center Drive (The Senior Center, Health and Wellness )has surpassed its 25 year life expectancy and is in need of full replacement. Components are beyond repair, have exceeded their life expectancy and or are obsolete. | Reduced maintenance costs, replacements will be serviceable and have a live of over 20 years |  | 2 |  |  |  | 725000 | 725000 | [5 empty] | 725000 | 725000 | [11 empty] | 725000
PW | 61 | Infrastructure Planning and Funding | Maintenance | Repair/Replacement of Exterior Walls,Gutters and Soffits at 999 Civic Center Drive | An exterior refresh of 999 Civic Center Drive is needed to assure the building envelope health. Tuckpointing, and cleaning of the brickwork is required in various areas of the building, the gutters and downspouts are in need of replacement, along with the water damaged soffit overhang in the rear of the building. | The exterior masonry, gutter system, and soffit overhang system at 999 Civic Center Drive are in disrepair and need immediate attention . Failure to replace or repair the the building envelope will result in damages caused by water intrusion and will continue to the damage the infrastructure prematurely. | Best practice roofing management will extend the life of the building and eliminate water intrusion |  | 2 |  |  |  | 250000 | 250000 | [5 empty] | 250000 | 250000 | [11 empty] | 250000
PW | 62 | Infrastructure Planning and Funding | Maintenance | Truck Wash Restoration | Reconfigure and plumb undercarriage wash, repair drainage, and reseal repaired concrete. | The undercarriage wash is in disrepair and requires plumbing upgrades and photo-eye activation. Additionally, the newly repaired concrete must be sealed in order to sustain its life expectancy. | Repairing the undercarriage wash will extend the life of our fleet's frame components, lowering maintenance costs and raising the likelihood of a high ROI when the vehicles are sold. Additional, the wash bay floors life will be extended and improver worker safety |  | 2 |  |  |  | 90000 | 90000 | [5 empty] | 90000 | 90000 | [11 empty] | 90000
PW | 63 | Infrastructure Planning and Funding | Maintenance | Full roof restoration at 7000 W. Touhy | Repair Adverse Membrane Conditions Present. Removal of Areas of Wet Insulation. Installation of New Perimeter and Penetration Flashings. Thorough Cleaning of Existing Membrane Surfaces. Application of New Restoration Treatment at Rates Specified. Application of New Surfacing Option | The roof system is original from the time the building was constructed in the early 2000s. Since the time of construction, the station has been experiencing severe leak issues in the main lobby area. It appears as though there are some drainage design issues, as well as, a composite wall paneling system that could have been improperly installed and experiencing saturation and deterioration. Failure to restore the roofing system will result in damages caused by water intrusion and will continue to the weaken the infrastructure prematurely. | A restoration of an existing roof is a lower cost alternate to full replacement estimated at $1,200,000. A restoration can extended the life of the existing roof system by 20-40 years (Fluid applied membrane can be applied more than once). |  | 2 |  |  |  | 310000 | 310000 | [5 empty] | 310000 | 310000 | [11 empty] | 310000
PW | 64 | Infrastructure Planning and Funding | Maintenance | Restoration vestibule stairs, walkway and guardrail at 7000 W. Touhy | Remove damaged pre-cast concrete from stairs and walkway, replace damaged metal frame work and guardrail, replace cement, paint and seal finished components. | The vestibule walkway, stairs and guardrail is badly corroded from winter conditions and needs restoration before complete system failure occurs | A restoration of an existing vestibule stairway is a lower cost alternate to full replacement |  | 2 |  |  |  | 200000 | 200000 | [5 empty] | 200000 | 200000 | [11 empty] | 200000
PW | 65 | Infrastructure Planning and Funding | Maintenance | Replacement of Exterior Door and Frames at PD Campus | Demolition and replacement of 5 exterior doors and framework of the PD Campus | The exterior doors and framework are badly corroded, potentially unsecure, and have past their life expectancy. | Increased security, improved aesthetic, improved envelope protection from weather. |  | 2 |  |  |  | 45000 | 45000 | [5 empty] | 45000 | 45000 | [11 empty] | 45000
PW | 66 | Infrastructure Planning and Funding | Maintenance | Replacement of Exterior Door and Frames at PW Campus | Demolition and replacement of 21 exterior doors and framework of the PW Campus | The exterior doors and framework are badly corroded, potentially unsecure, and have past their life expectancy. | Increased security, improved aesthetic, improved envelope protection from weather. |  | 2 |  |  |  | 170000 | 170000 | [5 empty] | 170000 | 170000 | [11 empty] | 170000
IT | 67 | Marketing and Communication | IT/Purchase | Audio Visual and Conference Room Improvements | A/V and conferencing systems update/refresh. | The current systems do not meet the user community demands to aid in collaboration and multimedia presentations. Many of our current A/V and conferencing systems at the Village Hall (Council Chambers, 1st and 2nd Floor conference rooms), Police Station (training room), Fitness Center, and Family Services (Multi-Purpose rooms) must be refreshed as they have gone past their useful life. | Improve collaboration and more productive meetings and presentations without being challenged due to outdated systems. | Negligible under 4% | 2 |  |  |  | 28000 | 28000 | [5 empty] | 28000 | 28000 | [11 empty] | 28000
IT | 68 | Infrastructure Planning and Funding | IT/Purchase | End-User Device Refresh Lifecycle | Refresh end-user desktops at the end of life 4~5 year cycle at the rate of 50 desktops a year. -This will include desktop or laptop and typical peripherals such as scanners, webcams, headsets, monitors, docking stations, software licenses, including end-point protection, i.e., antivirus and malware protection. | The village needs to be on a regular end-user device refresh life cycle to maintain its fleet of computers functional and in operating conditions. | Maintain efficient day-to-day operations of the Village administration and management. | $70,000. annual | 2 |  |  |  | 70000 | 70000 | [5 empty] | 70000 | 70000 | [11 empty] | 70000
IT | 69 | Infrastructure Planning and Funding | IT/Purchase | IT Infrastructure Improvements | Network and Wifi remedation | The Village's IT Network and WiFi infrastructure have been plagued with network outages that have crippled the staff's ability to utilize the IT network and Internet Services. Network remediation will address network availability and reliability. | Reliable Internet and network communications between and within the Village sites for all staff and guest users; | none *the operating maintenance budget will be realigned and offset existing costs. | 2 |  |  |  | 98000 | 98000 | [5 empty] | 98000 | 98000 | [11 empty] | 98000
IT | 70 | Infrastructure Planning and Funding | IT/Purchase | O365/M365 Migration | Office 365 migration | Currently, the Village hosts many Microsoft Enterprise services on-premises that have been less and less reliable and require a more advanced skill set to administer, manage, and current. The on-premises model has become unsustainable and is plagued with system outages. | Improve system and service availability and reliability for all stakeholders. By migrating to Office 365, the IT department will be better positioned to deliver IT services to Citizens, Staff, and businesses. Also, it would enhance our system uptime and security. | In the short run, as we migrate, there will be a nominal increase, but after a year, we will rebalance as we remove our technology debt and decommission systems. | 2 |  |  |  | 92600 | 92600 | [5 empty] | 92600 | 92600 | [11 empty] | 92600
IT | 71 | Infrastructure Planning and Funding | IT/Purchase | SCADA Security | Secure the Village's Supervisory control and data acquisition (SCADA) system. SCADA is a system of software and hardware elements that enables the Water Department to control industrial processes locally or at remote locations; Monitor, gather, and process real-time data; Directly interact with devices such as sensors, valves, pumps, motors, and more through human-machine interface (HMI) software; Record events into a log file; | The Village's SCADA system is vitally important tool for operating, managing, and monitoring public water. SCADA now has an ever-present role that includes looking after all automatic control and alarm management, logging of critical process data, and providing operators with remote access to equipment. In recent months the SCADA systems have been targets of cyber and ransomware attacks, it is more important than every to secure the SCADA system with network air-gap methodology. | Securing the Village's critical infrastructure Water Supply Plant from cyberattacks by minimizing vulnerabilities. | Less than 4% annual. | 2 |  |  |  | 36000 | 36000 | [5 empty] | 0 | [6 empty] | 36000 | [5 empty] | 36000
IT | 80 | Infrastructure Planning and Funding | IT/Purchase | End-User Device Refresh - CD | Refresh Community Development Department End-User Devices for Inspectors, and Managers. | Community Development staff utilizes technology to conduct inspections and permitting, the end-user devices for the department needs to be more flexible and mobile. The department is due for refresh of desktop, screens, scanners and printer. | Maintain efficient day-to-day operations of the Community Development functions and management thereof. |  | 2 |  |  |  | 30500 | 28000 | 500 | 500 | 500 | 500 | 500 | 28000 | 30500 | [11 empty] | 30500
PD | 4 | Infrastructure Planning and Funding | Project | Records Configuration - Going Paperless | Reconfiguring the Records Department to improve the work space design and digitization of the paper records. | Improving the work place design and digitization of the paper records will increase employees productivity and efficiency. It will also greatly reduce the space needed to physically store the records. If we continue to compile the paper arrest records, we will eventually run out of storage space. | The improved spatial arrangement should increase employee productivity, as well as decrease workplace tensions. Studies have shown that employees believe that effective workspace design will enhance their productivity. The digitization of the records will increase efficiency, by reducing the time to search for records. It will also greatly reduce the amount of space needed to store the records. | Phase 1: Shelving - approximately $2,100 Phase 1: Cages - approximately $5,300 Phase 2: Digitization - approximately $60,000 | 3 |  |  |  | 70000 | 70000 | [5 empty] | 70000 | 70000 | [11 empty] | 70000
PW | 9 | Infrastructure Planning and Funding | Project | Bike & Ped Update (Project Name/Scope TBD) | A variety of capital projects have been recommended by the BPAG as part of the bike and pedestrian plan update. The top priority project is not yet know. | A variety of capital projects have been recommended by the BPAG as part of the bike and pedestrian plan update. The top priority project is not yet know. | The project will increase bicycle and pedestrian safety | FY23 $50,000 Design Engineering FY24-FY27 $450,000 Construction The cost and schedule is dependent on BPAG recommendation and grant funding | 3 |  |  |  | 500000 | 50000 | 90000 | 90000 | 90000 | 90000 | 90000 | 50000 | 500000 | [11 empty] | 500000
PW | 14 | Infrastructure Planning and Funding | Project | Milwaukee Avenue Crossing (Jonquil/Monroe) | Pedestrian safety crossings at the intersection of Milwaukee Avenue with Jon Quil Terrace and Monroe Street $1,600,000 Estimated construction and construction engineering cost $294,000 Estimated design engineering cost | The 2014 Bike and Ped plan identified the intersections of Jon Quil Terrace and Monroe Street as locations that would benefit from pedestrian safety improvements. The BPAG has supported further study of these locations | The project will increase pedestrian safety | Previous funding: $4,500 for Warrant Study FY 22 Phs1 budgeted $135,000 (Not awarded due to scope questions) FY23 or FY 24 Phs 2 Engineering $150,000 FY25 or later Budget impact: $300,000 construction local match Schedule is dependent on IDOT and grant funding | 3 |  |  | 4500 | 585000 | 135000 | 150000 | 300000 |  |  |  | 135000 | 585000 | [10 empty] | 1309000 | 1894000
FD | 72 | Infrastructure Planning and Funding | IT/Purchase | Purchase New Ambulance | Replace heavily used and worn out ambulance from 2009. A new ambulance will allow for a reliable vehicle to respond to medical emergencies without delay. | This ambulance will replace an aging ambulance that is worn out and encountering increased annual maintenance costs. The ambulance being replaced is over ten years old. The fire department standard is to operate an ambulance five years in front line status and five years in backup status. | A newer ambulance provides improved comfort and reliability for those being transported. It will reduce annual maintenance costs. It will allow operations at the current modern standard of medical care. |  | 2 |  |  |  | 325000 | 325000 | [5 empty] | 0 | [7 empty] | 325000 |  |  |  |  | 325000
FD | 73 | Infrastructure Planning and Funding | IT/Purchase | Purchase New Fire Engine | Replacement of aging and deteriorating 1992 fire engine. | The existing engine is very old, rusted and struggles with maintenance repairs. Parts are being difficult to find for this vehicle. | Having a reliable fire apparatus will allow the fire department to effectively maintain its operations. |  | 2 |  |  |  | 875000 | 875000 | [5 empty] | 0 | [7 empty] | 875000 |  |  |  |  | 875000
PW | 74 | Infrastructure Planning and Funding | IT/Purchase | Replace (11) Civic Center Vehicles with (8) Electric "Motor Pool" Vehicles | Replace (11) General Government Vehicles, (10) 2007 Ford Fusions and (1) 2000 Crown Victoria with (8) Electric "Motor Pool" Vehicles. This project will also include charges that will be installed by the Village Electrician. | Replace (11) General Government Vehicles, (10) 2007 Ford Fusions and (1) 2000 Crown Victoria with (8) Electric "Motor Pool" Vehicles. This project will also include charges that will be installed by the Village Electrician. | The General Government and Code vehicles will be stored at Village Hall and are the perfect candidate for an electric fleet. The vehicles are not used for long distances and can be charged over night while parked at Village Hall. |  | 2 |  |  |  | 400000 | 400000 | [5 empty] | 0 | [7 empty] | 400000 |  |  |  |  | 400000
PW | 75 | Infrastructure Planning and Funding | IT/Purchase | Replace (2) Detective Sedans Units #104 and #107 | Replace (2) 2007 Dodge Charger Sedans with (2) 2023 Police SUV's | The rear wheel drive detective sedans are not well suited for winter service and must be replaced with an all wheel drive vehicle. Furthermore, the vehicles are beyond their service life and have proven to be unreliable for emergency service | Reduced maintenance, increased safety, increased officer ergonomics. |  | 1 |  |  |  | 90000 | 90000 | [5 empty] | 0 | [7 empty] | 90000 |  |  |  |  | 90000
PW | 76 | Infrastructure Planning and Funding | IT/Purchase | Replace (2) Water Department Trucks Units #440 and #472 | Replace (2) Water Department trucks 2008 and 2006 models with (2) 2023 Utility Body trucks. The replacement vehicles will be built on Ford F-350 Chassis and Knapheide service bodies that will be used by the water department for service calls and for winter snow removal operations. | 440 and 472 are badly corroded, past their service life and require replacement. | Reduced maintenance, increased safety, increased officer ergonomics. |  | 2 |  |  |  | 170000 | 170000 | [5 empty] | 0 | [7 empty] | 170000 |  |  |  |  | 170000
PW | 77 | Infrastructure Planning and Funding | IT/Purchase | Build (4) Hooklift attachments for PW Trucks | In lieu of full truck replacements for specialty equipment, 4 Hooklift attachments will be built to serve multiple areas of the Public Works Operation. An asphalt "hot box" body, a Chipper Box, A Watering and De-Icing Tanker and a Flat Bed Trailer | The interchangeable attachments allows us replace only the working components of the truck and not the entire truck itself. The package allows for the working capacity of 4 trucks for the cost of 1. This practice will save the village over $500,000 in truck costs alone. | Reduced maintenance, increased safety, increased officer ergonomics. |  | 1 |  |  |  | 310000 | 310000 | [5 empty] | 0 | [7 empty] | 310000 |  |  |  |  | 310000
PW | 78 | Infrastructure Planning and Funding | IT/Purchase | Replace Sewer Department Van #478 | Replacement of Water Department Cube Van #478 2008 Chevrolet E3500 Upfit with Morgan Olsen Route Star Walk-In Van body and applicable hardware for water main repairs. | 478 has past its service life and requires replacement. | Reduced maintenance, increased safety, increased ergonomics. |  | 1 |  |  |  | 180000 | 180000 | [5 empty] | 0 | [7 empty] | 180000 |  |  |  |  | 180000
PW | 79 | Infrastructure Planning and Funding | IT/Purchase | 499 Street Sweeper Replacement | Replacement unit will serve as the primary street sweeper for sweeping and leaf pickup operations | The 14-year-old street sweeper has exceeded its life expectancy and has proven unreliable to the Street Department. 499 has suffered multiple breakdowns that needed costly heavy-duty tows during critical clean-up situations, such as leaf pick up, three times this year. | Reduced maintenance costs, elimination of costly $10,000 winter rebuilds, increased duty cycle, lower carbon footprint by way of increasing fuel efficiency. |  | 1 |  |  |  | 300000 | 300000 | [5 empty] | 0 | [7 empty] | 300000 |  |  |  |  | 300000
PW | 19 | Infrastructure Planning and Funding | Project | Green Alley Project | The Green Alley location is TBD | The FY22 budget includes the design of a Green Alley. The Village often pursues green infrastructure grant funding and having a shovel ready project increases the likelihood of receiving funding. Construction schedule is pending grant funding. Likely not earlier than FY24 | The project will reduce flooding in Niles. The project will increase sustainability in Niles. | Project will likely result in a reduction in the amount of calls for service received. Permeable pavers would likely result in additional maintenance. | 3 |  |  |  | 600000 |  |  | 600000 |  |  |  | 300000 | 300000 | [10 empty] | 300000 | 600000
PW | 81 | Infrastructure Planning and Funding | Project | Complete lead service line replacement utilizing IPA forgivable loans | Complete replacement of lead services lines as part of Lead Service Line Replacement Program | HB-3739 created a statutory requirement for the Village to completely replace lead service lines when they are disturbed. Partial replacement of lead service lines present a public health issue. The Village is working on a lead service line replacement plan which must be completed by 2024. Approximately 4000 lead services in town will need to be replaced over a 17 year period However as an interim policy the lead services that are disturbed after January 1, 2022 must be replaced in full. | The project will eliminate a public health hazard in Niles and improve the marketability of our housing stock.. Utilization of low interest of forgivable IEPA loans presents the lowest cost financing solution to this problem. | The annual cost to our water fund will be in the range of $4,000,000/year however a portion to all of the loan costs will be forgivable. FY23 -FY27$4,000,000, The Village would potentially be required to front the payments and request loan disbursement reimbursement | 1 |  |  |  | 20000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 |  | 0 | [6 empty] | 10000000 |  |  |  |  | 10000000 | 20000000
PW | 82 | Infrastructure Planning and Funding | Project | Touhy Avenue Watermain Replacement | Touhy Avenue watermain replacement from Caldwell to Lehigh | The 2016 Water System Master Plan specifically recommended the replacement of the Touhy Avenue watermain to improve fire protection service level FY 23 $200,000 for design engineering FY 25 $3,800,00 for construction | The project will reduce water loss, reduce the frequency of water main breaks, improve system reliability, improve valve interoperability, improve water quality, improve fire flow, improve system pressure, and increase the overall value of the water system. | Watermain replacement reduces operational cost related to water loss and emergency watermain break repair. | 1 |  |  |  | 4000000 | 200000 | 3800000 |  |  |  |  | 0 | [12 empty] | 0
PW | 83 | Infrastructure Planning and Funding | Project | Watermain Replacement Program FY24-FY27 | Watermain replacement for end of service life watermains | The Matrix study as well as the 2016 Water System Master Plan recommended the replacement of 1.3%-2% per year according to ASCE industry standards. This equates to 1.3-2 miles of watermain replacement per year. The following minimum recommended budget allocation made based on historic program expenditures: FY24 -FY27 $2,000,000/year | The project will reduce water loss, reduce the frequency of water main breaks, improve system reliability, improve valve interoperability, improve water quality, improve fire flow, improve system pressure, and increase the overall value of the water system. | Watermain replacement reduces operational cost related to water loss and emergency watermain break repair. Annual expenditure should be based on the ability to pay for the work as determined as a result of a rate study. | 1 |  |  |  | 8000000 |  | 2000000 | 2000000 | 2000000 | 2000000 |  | 0 | [12 empty] | 0
PW | 84 | Foster Community Identity | IT/Purchase | Holiday Decorations |  |  |  |  | 2 | [10 empty] | 0 | [12 empty] | 0
PW | 85 | Infrastructure Planning and Funding | Maintenance | Post-Bond Street Improvement Maintenance | Funds designated for street maintenance after the 2022 street improvement bond money has been spent. | Over the course of the next 4-5 fiscal years, the PW department will use bond funds to repair streets in an attempt to improve the pavement condition index (PCI) to a level of 65. Subsequent to that, staff expect an annual maintenance cost of around $900,000 to maintain that level of pavement condition into the future. |  |  | 1 | [8 empty] | 900000 | 900000 | 0
[12 empty] | 2411447 | 113430687.36 | 21357264.56 | 29864684.56 | 17609684.56 | 11094684.56 | 11319684.56 | 15109684.56 | 7122385.38 | 17437244.18 | 141980 | 3890000 |  | 6680000 | 2897810 | 26685050 | 2730000 | 1150000 | 0 | 14800000 | 36410900 | 117302984.18
FitnessProject Costs
Police Memorial/Room Redesign
Auto Fund transfer formula
project tags
Note on A1: Department Abbreviations: Department: PW - Public Works PD - Police FD - Fire FC - Fitness Center SC - Senior Center FS - Family Services CD - Community Development FIN - Finance IT - Information Technology AD - Administration
Note on C1: STRATEGIC PRIORITY AREA: This is define in the Strategic Planning document and consists of one or more of the following: 1) Financial Stability and Transparency; 2) Diversified Economic Development; 3) Marketing and Communication; 4) Infrastructure Planning and Funding; 5) Foster Community Identity.
Note on J1: Schultz, Conor: Tier 1: Must-Have projects to be completed for stability of services Tier 2: Resources (financing and capacity) are available for the designated budget year Tier 3: Stretch goal/Resources Unavailable/Further Clarification Required
Note on L1: Overall Institution Rank.
Note on E3: Schultz, Conor: preexisting plan
Note on M5: Schultz, Conor: Engineering Phase 1 and 2 already completed; $30,000 Invest in Cook Grant
Note on N5: Schultz, Conor: Project is programmed for CMAQ ($375,000) and Invest in Cook Funding ($112,500)
Note on V5: Schultz, Conor: Local costs remaining after grants
Note on AG5: Schultz, Conor: $375,000: CMAQ $112,500: Invest in Cook $30,000: Invest in Cook prior spending
Note on V6: Schultz, Conor: Niles Share--rest is Morton Grove
Note on AG7: Schultz, Conor: HSIP -$909,000 ITEP- $2,000,000 CMAQ/RTA - $640,000 Local $750,000
Note on O8: Schultz, Conor: design engineering
Note on E16: Schultz, Conor: potential to split Caldwell into separate project
Note on M16: Schultz, Conor: engineering to date
Note on N16: Schultz, Conor: estimations; see FUND IMPACT
Note on O16: Schultz, Conor: FY 23 budget impact $750,000-$1,500,000
Note on Z16: Schultz, Conor: may change; see comments; federal funding may also be available
Note on AG17: Schultz, Conor: DCEO application: $1.8m
Note on E22: Schultz, Conor: Cost of construction/renovation outstanding
Note on I23: Schultz, Conor: additional funds ($35,000+) already in hand?
Note on AG25: Schultz, Conor: MWRD - Project will pursue $2 million grant from MWRD in CY24 Project is likely eligible an IEPA Low Interest Loan Scope at Harlem eligible for STP and/or IDOT funding
Note on M26: Schultz, Conor: engineering design
Note on AG26: Schultz, Conor: MWRD Grant being sought
Note on O27: Schultz, Conor: design engineering
Note on P27: Schultz, Conor: construction
Note on V27: Schultz, Conor: could also be Capital or MFT
Note on R28: Schultz, Conor: Local Match
Note on S28: Schultz, Conor: Local Match
Note on Z28: Schultz, Conor: Historically Niles has funded Phs 1 engineering with MFT funds to improve chances of receiving federal funding in later phases. This project has a high probabilty of obtaining federal funding
Note on E30: Schultz, Conor: Tom has a list of identified roads/projectsfor the first two years of the bond
Note on N30: Schultz, Conor: may be lower, down to $15m
Note on AG30: Schultz, Conor: ARPA Funding
Note on E36: Schultz, Conor: Talk to Linda/Ernie about cost estimates for these
Note on E52: Schultz, Conor: tieto VillageHall Entrance
Note on AA54: Schultz, Conor: G/P Touhy
Note on AB69: Schultz, Conor: because the item is relevant to water operations, this will be included in the water Fund
Note on V72: Schultz, Conor: also assignable to the Capital Projetcs Fund or MFT Fund
Note on M73: Schultz, Conor: warrant study
Note on O73: Schultz, Conor: originally in FY21 budget
Note on V73: Schultz, Conor: Village share
Note on AG73: Schultz, Conor: HSIP, CMAQ, and TAP-L federal funding will be pursued.

## Summary CIP
Dept. ID | Project # | SP Area | SP Area Secondary Category | CIP Category | Project Title | Description | Justification | Impact | Fund Impact | Priority Tier | Elected Priority | Project Rank | Sunk Cost | Cost Total | FY23 | FY 24 | FY 25 | FY 26 | FY 27 | FY 28 | GF FY23 | General Fund | Fitness | Capital Fund | MFT | TIF | Water Fund | Auto Fund | Cash | Loan | Bond | Grants | Funding Total | SP Area
PW | 1 | Infrastructure Planning and Funding | Blank | Project | USACE Funded Stormwater Project | The Stormwater Commission will meet on 12/13/21 to select a project to receive USACE (Army Corps of Engineers) funding. | The project was identified in the 2018 Stormwater Master Plan update at a top quartile project. The project advancement is expected to be recommended by the Stormwater commission. Potential projects include: 17-4, 17-3, 17-9B,17-14B Target construction cost $900,000 FY24 Federal cost Local Share $331,250 includes $200,000 FY23 - Engineering Design | The project will reduce flooding in Niles. | Project will likely result in a reduction in the amount of calls for service received. | 3 |  |  |  | 331250 | 331250 | [5 empty] | 0 | [5 empty] | 331250 |  |  |  |  | 331250 | 662500 | Financial Stability and Transparency
PW | 2 | Infrastructure Planning and Funding | Blank | Project | Implementation of Entrance and Roadway Signage Plan | In 2016, a comprehensive plan was developed for the installation of various signage throughout the Village, including entrance signage and roadway signage identifying Niles and wayfinding to key points within Niles. | Signage assists with branding, economic development and the overall aesthetics of Niles. | Economic development and improved aesthetics. | This is a multi-year project with varying costs each year dependent on which signage is being constructed and/or erected. These costs will be determined by which construction projects are scheduled for many of the key locations. | 1 |  |  |  | 404000 | 404000 | [5 empty] | 404000 | 404000 | [10 empty] | 404000 | Diversified Economic Development
PD | 3 | Infrastructure Planning and Funding | Blank | Project | Police Training Room Update | Update IT equipment including: replacing existing control tower with modern control function, create "one touch" system, create wireless Bluetooth connection, create wireless microphone system to be used by instructors and presenters, capability of displaying different outputs (linking with VON cameras i.e. LPR's surveillance cameras, etc.). Lastly, replacing stained carpet and adding electrical outlets to the floor. | Currently, the PD training room IT equipment is difficult to work and only a few people in the department know how to operate the system. If these individuals are not here, other PD members are not able to utilize the control systems. When you plug in the HDMI cable to the laptop the system needs to be reset. The control plane on the wall has never worked. The PD training room hosts visitors for classes and for cake and coffee for retirement parties. The carpet is badly stained beyond cleaning capabilities and gives a negative impression of the PD when there are visitors. Additionally, when the PD replaces the carpet with new flooring, that is the ideal time to install outlets on the floor | The completion of this project will bring the NPD into the 21st century and NPD staff and instructors will be able to utilize the training room with ease. The system in place is very complicated to use and only a few staff members know how to operate the system. The carpet in the training room has been cleaned numerous times and the carpet is stained beyond cleaning capability. When the carpet is replaced, it is the best time to add electrical outlets into the floor for visitors to plug in their laptops for training. |  | 3 |  |  |  | 0 | tbd | tbd | tbd | tbd | tbd | tbd | 0 | [11 empty] | 0 | Marketing and Communication
PD | 4 | Infrastructure Planning and Funding | Blank | Project | Records Configuration - Going Paperless | Reconfiguring the Records Department to improve the work space design and digitization of the paper records. | Improving the work place design and digitization of the paper records will increase employees productivity and efficiency. It will also greatly reduce the space needed to physically store the records. If we continue to compile the paper arrest records, we will eventually run out of storage space. | The improved spatial arrangement should increase employee productivity, as well as decrease workplace tensions. Studies have shown that employees believe that effective workspace design will enhance their productivity. The digitization of the records will increase efficiency, by reducing the time to search for records. It will also greatly reduce the amount of space needed to store the records. | Phase 1: Shelving - approximately $2,100 Phase 1: Cages - approximately $5,300 Phase 2: Digitization - approximately $60,000 | 3 |  |  |  | 70000 | 70000 | [5 empty] | 70000 | 70000 | [10 empty] | 70000 | Infrastructure Planning and Funding
PD | 5 | Infrastructure Planning and Funding | Foster Community Identity | Project | Niles Law Enforcement Memorial | The statue titled “The Protector”, will feature a police officer standing atop a pedestal saluting. An officer’s salute exhibits a long standing gesture of friendship, confidence and professionalism which is intended to honor all police officers killed in the line of duty, especially Niles Police Officer Steven Zourkas who was killed in the line of duty in 2005. | This display shall pay tribute to every police officer serving communities throughout the country and shall serve as a visual reminder of the commitment by the Village of Niles to remember the fallen. The Committee is working hard to effectuate the Village’s unwavering support for all members of law enforcement. | The Niles Law Enforcement Memorial statue is being built to pay tribute to police officers that have made the ultimate sacrifice for the communities they serve, and to honor police officers that put their lives on the line everyday protecting the communities they are sworn to serve. This is of special significance to the Niles Police Department having lost Officer Steven Zourkas in the line of duty in 2005. | Total project cost: $95,000.00. Public Works will be covering demolition, excavation and hauling of debris, electrical work, site utilities landscaping and some concrete work, which will cost approximately $20,000.00-$35,000.00. Anything beyond $35,000.00, will be paid for through donations by the Niles Law Enforcement Memorial Committee. | 2 |  |  |  | 35000 | 35000 | [5 empty] | 35000 | 35000 | [10 empty] | 35000 | Foster Community Identity
PD | 6 | Infrastructure Planning and Funding | Blank | Project | Automated License Plate Reader program | This project involves the purchase of 12 Automated License Plate reading cameras as well as updating our 2 current license plate reading cameras. The price includes all hardware and software as well as installation. The system will also allow our Axon squad car cameras to function as mobile License plate readers. | License plate reading cameras (LPR) are an essential tool in fighting crime and protecting both our residents and businesses. The LPR system will provide the Niles Police Department with analytics and access to billions of license plate scans from our LPR cameras as well as cameras that are deployed in cities throughout the country. The information provided by the LPR cameras will be invaluable for all types fo crimes that occur within the Village of Niles. For example, an armed robbery occurs and the offender flees in a vehicle. A witness of victim and provide a vehicle description and a partial license plate. That information can be entered and investigators would have instant access to images of vehicles matching the description. | This project will provide the following benefits:Assist in locating carjacked vehicles and increase the likelihood of locating offenders. LPR cameras will assist in combating drug trafficking "hot spots" within the village by using convoy analysis. LPR's will help to combat and disrupt catalytic converter and vehicle thefts by using associate analysis and identifying vehicles that frequently travel together. The LPR system will assist in locating suspects that fell by using the comprehensive plate location analysis as well as the use of predictive analytics and historical vehicle location data. Burglary investigations will benefit from the use of common license plate analysis to generate a suspect via previously observed vehicles in areas of recent burglaries. LPR cameras will placed in corridors that have statistically high numbers of DUI's providing increased assistance in our DUI enforcement. | This purchase will have an initial impact of $38,896.00 and a recurring impact of $34,396.00. | 2 |  |  |  | 210876 | 38896 | 34396 | 34396 | 34396 | 34396 | 34396 | 38896 | 210876 | [10 empty] | 210876 | Blank
PW | 7 | Infrastructure Planning and Funding | Blank | Project | Public Works Salt Dome & Storage Facility (Phase 2 & 3) | Public works salt dome replacement & storage facility. | The public works salt dome needs to be replaced. The current salt dome is failing. There are structural problems that cant be fixed. Along with structural concerns, the salt dome is under sized. In conjunction with the salt dome being replaced, the current storage facility is failing. Major structural repairs are needed. Both issues need to be resolved at the same time. In order for the salt dome to be rebuilt, infrastructure needs to be relocated to where the storage facility garage is located. Once completed, the new storage garage can be rebuilt. This project has gone before the Public Works Committee and a power-point presentation was given to the Mayor and Finance Committee. This project is per the Public Works Campus Master Plan completed in 2017. | A new salt dome would increase safety for staff. Loading the salt dome with a front end loader is not the safest way of pushing in salt. Vehicles have tipped over inside the salt dome on multiple occasions. The current salt dome is failing due to roof damage and concrete damage. Many of these issues are past simply repairing them. The salt dome is undersized. Clear Roads Best Management Practices states that a salt dome should hold 150% of annual usage. The salt dome only holds approximately 1800 tons of salt. Niles averages 3,871 tons per year. The new salt dome would hold approximately 6,413 tons of salt. This would allow the village to purchase salt using off season pricing. There would be a considerable price difference. Currently staff is purchasing salt at peak usage and runs the risk of not being able to acquire salt. | There will be a reduction is salt purchasing cost as staff will not need to purchase salt during peak times. Overtime will be reduced for salt deliveries. Reduction in temporary repair costs associated with failing building and salt dome. | 2 |  |  |  | 3890000 | 190000 | 2000000 | 1700000 |  |  |  | 0 |  |  | 3890000 | [8 empty] | 3890000
FD | 8 | Infrastructure Planning and Funding | Blank | Project | Fire Station #2 | This is a multi-phase project to replace the aging and failing fire station 2 building. This project includes feasability analysis to determine building and land needs, as well as architectural design, possible land acquisition and construction. | The existing fire station is approaching sixty years old and the building infrastructure continues to fail on a regular basis. This includes roof leaks, plumbing, electrical and structural issues. The cost of maintenance to keep the existing building functional is pushing the cost/benefit towards building replacement. In addition, the needs of the fire department have changed over the years and modernization is essential to moving forward with fire department operations, including the ability to fit modern fire apparatus in the fire station. | In addition to reducing annual building maintenance costs, a new fire station will allow the fire department to adapt to modern demands, including the space for modern fire apparatus. |  | 3 |  |  |  | 14000000 |  |  | 14000000 |  |  |  | 0 | [11 empty] | 0
PW | 9 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Bike & Ped Update (Project Name/Scope TBD) | A variety of capital projects have been recommended by the BPAG as part of the bike and pedestrian plan update. The top priority project is not yet know. | A variety of capital projects have been recommended by the BPAG as part of the bike and pedestrian plan update. The top priority project is not yet know. | The project will increase bicycle and pedestrian safety | FY23 $50,000 Design Engineering FY24-FY27 $450,000 Construction The cost and schedule is dependent on BPAG recommendation and grant funding | 3 |  |  |  | 500000 | 50000 | 90000 | 90000 | 90000 | 90000 | 90000 | 50000 | 500000 | [10 empty] | 500000
PW | 10 | Infrastructure Planning and Funding | Diversified Economic Development | Project | North Branch Trail Connection - Bunker Hill | Trail Connection from the intersection of Touhy and Caldwell to the North Branch Trail $560,000 construction costs $20,000 redesign $49,600.82 Engineering expenditure to date ($30,000 grant reimbursed) | This project was originally conceived as an economic development project to direct bike traffic from the busy North Branch Trail to the Touhy Triangle. The BPAG has supported the project. | The project will increase pedestrian safety and interconnection to the North Branch Trail | Previous funding: $49,600.82 for Phs 1 and Phs 2 engineering FY23 $112,500 Local match | 1 |  |  | 49600.82 | 580000 | 580000 | [5 empty] | 112100.82 | 112100.82 | [9 empty] | 517500 | 629600.82
PW | 11 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Oakton Street Pedestrian network connections | Pedestrian network connections from the Chesterfield Gardens neighborhood to the newly pedestrian improved intersection of Caldwell and Oakton | The BPAG has supported the project and is expected to be included in the recommended projects as a result of the bike and pedestrian plan update. | The project will increase pedestrian safety and interconnection to the Oakton Street mulitmodal trail | FY23 $30,000 Design Engineering Fy24 $ 170,000 Construction | 2 |  |  |  | 200000 | 30000 | 170000 |  |  |  |  | 30000 | 200000 | [10 empty] | 200000
PW | 12 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Oakton Street and Caldwell Avenue - Multimodal improvements | Off street pedestrian and multimodal improvements on CALDWELL AVENUE (FAU 0376) & OAKTON STREET (FAU 1332) FROM VAPOR LANE TO I-94 EDENS EXPRESSWAY Morton Grove is leading this project and Niles is only responsible for cost sharing. Niles share is estimated at $260,000 total | Following resident outreach the Village of Skokie, Morton Grove, and Niles formed a partnership to pursue funding of pedestrian improvements from the intersection of Caldwell and Oakton to Niles West High school. The BPAG has been generally supportive of the project. | The project will increase pedestrian safety | Previous funding: $40,000 for Phs 1 engineering cost share FY23 $220,000 FY24TBD Schedule is dependent on IDOT | 1 |  |  | 40000 | 220000 | 220000 | [5 empty] | 220000 | 220000 | [9 empty] | 2860400 | 3080400
PW | 13 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Golf Road, Milwaukee Avenue, and Greenwood Avenue - Sidewalk Infill | The Village is in the process of designing sidewalk infill from on Golf Road from Dee Road to Washington Road, on Greenwood Avenue from Golf Road to Sunset Road, and Milwaukee Avenue from Golf Road to Maryland Street. $299,079.52 Engineering Design to date $3,400,000 Estimated construction cost, $340,000 Construction Engineer | Golf Road and Greenwood Avenue have been subject to multiple pedestrian fatalities in the past 10 years. Sidewalk is missing in multiple locations which can result in pedestrian walking in the roadway. The sidewalk infill will provide a safer and more accessible space for pedestrians on these routes. | The project will increase pedestrian safety | Previous funding: $299,079.52 for design FY 23 Budget impact: $200,000 Land Acquisition FY 24 Budget impact: $750,000 Local Match Schedule is dependent on ROW certification | 1 |  |  | 299079.52 | 950000 | 200000 | 750000 |  |  |  |  | 200000 | 950000 | [9 empty] | 4299000 | 5249000
PW | 14 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Milwaukee Avenue Crossing (Jonquil/Monroe) | Pedestrian safety crossings at the intersection of Milwaukee Avenue with Jon Quil Terrace and Monroe Street $1,600,000 Estimated construction and construction engineering cost $294,000 Estimated design engineering cost | The 2014 Bike and Ped plan identified the intersections of Jon Quil Terrace and Monroe Street as locations that would benefit from pedestrian safety improvements. The BPAG has supported further study of these locations | The project will increase pedestrian safety | Previous funding: $4,500 for Warrant Study FY 22 Phs1 budgeted $135,000 (Not awarded due to scope questions) FY23 or FY 24 Phs 2 Engineering $150,000 FY25 or later Budget impact: $300,000 construction local match Schedule is dependent on IDOT and grant funding | 3 |  |  | 4500 | 585000 | 135000 | 150000 | 300000 |  |  |  | 135000 | 585000 | [9 empty] | 1309000 | 1894000
PW | 15 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Pedestrian Safety Improvements at Caldwell and Cleveland; Wauekgan and Cleveland | The Village is in the process of designing pedestrian crossing improvements at the above intersections. $85,486.66 Engineering Expenditure to date $250,000 Estimated cost for final design and construction engineering $1,900,000 estimate for construction | The Amling memorial trail follows Cleveland Street where it crosses Waukgan Road and Caldwell Ave. The intersections have long been slated for pedestrian safety improvements. More recently the BPAG has recommended improvements are installed and has been involved in the design development process. | The project will increase pedestrian and bicycle safety; check on MFT fund balance; | Previous funding: $85,486.66 for design; project cost increase to $2,000,000 FY 23 budget impact $750,000-$1,500,000 Schedule is dependent on IDOT review. Federal funding eligible but that increases the project timeline 3-4 years | 2 |  |  | 85486.66 | 2000000 | 1000000 | 1000000 |  |  |  |  | 0 |  |  |  | 2000000 | [7 empty] | 2000000
PW | 16 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Touhy Avenue at Gross Point Road Intersection Improvements | Intersection improvement at Touhy and Gross Point Road. The improvement include a multimodal trail, roadway widening, left turn lanes, and lighting. Construction Cost estimate: $3,400,000 | The intersection at Touhy and Gross point has a skew angle and the lack of left tuyrn lanes that make the intersection unsafe. In addition there is a lack of coherent pedestrian route on Touhy from Gross Point Road to Caldwell Avenue. | The project will increase bicycle safety with offstreet multimodal trail. The project will increase roadway safety with left turn lanes and lighting. The project will increase pedestrian safety by completing infill on Touhy Ave. | FY23 $160,000 Local Match FY23 $340,000 Phs 3 engineering (80% reimbursable) Previous expenditure: (LA Services $178,519; Phs 2 Design $223,813; Land Acquisition $1,045,000, Phs 1 Engineering $111,152) | 1 |  |  | 1558484 | 500000 | 500000 | [5 empty] | 500000 | 500000 | [9 empty] | 3200000 | 3700000
PW | 17 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Shermer Road - Rehabilitation and Multimodal Improvements | Rehabilitation of Shermer Road from Waukegan north to Village Limit. Project includes on-street bike and improvements per 2014 Bike and ped plan | 2018 State of the Streets report indicates Shermer is due for rehabilitation Project includes on-street bike and improvements per 2014 Bike and ped plan | The project will increase bicycle safety and pavement is at the end of its useful life | FY23 $180,000 Phs 1 engineering Fy 24 $180,000 Phs 2 engineering FY26-27 $360,000 Local match | 2 |  |  |  | 1080000 | 180000 | 180000 |  | 360000 | 360000 |  | 180000 | 900000 |  |  | 180000 | [7 empty] | 1080000
PW | 18 | Infrastructure Planning and Funding | Blank | Project | Lead Service Line Replacement | Complete replacement of lead services lines which require emergency repair | HB-3739 created a statutory requirement for the Village to completely replace lead service lines when they are disturbed. Partial replacement of lead service lines present a public health issue. The Village is working on a lead service line replacement plan which must be completed by 2024. However as an interim policy the lead services that are disturbed after January 1, 2022 must be replaced in full. The Public Works committee will consider this issue on 12/17/21 | The project will eliminate a public health hazard in Niles and improve the marketability of our housing stock. | The annual cost to our water fund will be in the range of $500,000 to $600,000 depending on how many repairs are required each year. FY23 $600,000, FY24 $600,000, FY25$600,000, FY26 $600,000, FY27 $600,000 | 1 |  |  |  | 3600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | [5 empty] | 3600000 | [5 empty] | 3600000
PW | 19 | Infrastructure Planning and Funding | Blank | Project | Green Alley Project | The Green Alley location is TBD | The FY22 budget includes the design of a Green Alley. The Village often pursues green infrastructure grant funding and having a shovel ready project increases the likelihood of receiving funding. Construction schedule is pending grant funding. Likely not earlier than FY24 | The project will reduce flooding in Niles. The project will increase sustainability in Niles. | Project will likely result in a reduction in the amount of calls for service received. Permeable pavers would likely result in additional maintenance. | 3 |  |  |  | 600000 |  |  | 600000 |  |  |  | 300000 | 300000 | [9 empty] | 300000 | 600000
PW | 20 | Infrastructure Planning and Funding | Foster Community Identity | Project | Touhy Bridge Project - Local Improvements | The Village is responsible for various non-participating costs related to the Touhy Bridge project. | Per July 2018 Letter of intent the Village made a commitment to fund the folowing project elements: Watermain relocation, emergency vehicle preemption, Private benefit traffic signal, roadway lighting, aesthetic bridge imporvements. | The project will increase bicycle safety. The aesthic improvements to the bridge have been requested by multiple elected officials | FY23-FY24 $650,000 | 1 | x |  |  | 650000 |  | 650000 | [5 empty] | 650000 | [10 empty] | 650000
PW | 21 | Infrastructure Planning and Funding | Foster Community Identity | Project | Caldwell Avenue Niles sign and lighting | Niles branded sign on the Caldwel Avenue Bike Bridge. Painting of Bridge, railing rework and lighting | The existing Caldwell Bike Bridge is very under stated and are not celebrated. The elected officials have requested an entrance banner sign is placed on the existing bridge. | The project will improve aesthetics to support redevelopment and beautify the Village. | There will be minor addition to electricity costs FY23 $300,000 Construction cost | 1 | x |  |  | 300000 | 300000 | [5 empty] | 300000 | 300000 | [10 empty] | 300000
PW | 22 | Infrastructure Planning and Funding | Foster Community Identity | Project | Bridge Flag Poles | Installation of Flag Poles at various Chicago River Bridges in Town. Including: Howard Street, Touhy Avenue, and Hart Road | The existing Chicago River Bridges in town are very under stated and are not celebrated. The elected officials have requested flag poles are placed at the approaches to the bridges. | The project will improve aesthetics to support redevelopment in the area. The project will celebrate the bridges and create a community identifier for Niles | FY23 - $40,000 FY24 - $80,000 There will be minor addition electricity costs as well flag replacement and manpower for operating the poles | 1 | x |  |  | 120000 | 40000 | 80000 |  |  |  |  | 40000 | 120000 | [10 empty] | 120000
PW | 23 | Infrastructure Planning and Funding | Blank | Project | Lawrencewood Gardens and Oasis Neighborhood Storm Sewer Improvement | Storm sewer Improvement from Mulford and Octavia to Howard Street Storm sewer outfall | The project was identified in the 2018 Stormwater Master Plan update at a top quartile project. Stormwater Project # 17-7a The project advancement was recommended by the Stormwater commission. The high cost of this project requires the establishment of a stormwater utility. Schedule is dependent on grant funding or other revenue source. Project should be projected for FY28 due to the size and scope. | The project will reduce flooding in the Lawerencewood Gardens and Oasis Neighborhoods The project is an extension of the Howard Street Outfall | Project will likely result in a reduction in the amount of calls for service received from the Lawerencewood Gardens and Oasis Neighborhood; potential SSA funding | 3 |  |  |  | 10400000 | [5 empty] | 10400000 | 0 | [5 empty] | 10400000 |  |  |  |  | 2000000 | 12400000
PW | 24 | Infrastructure Planning and Funding | Blank | Project | Oketo Avenue Stormwater Improvement | Oketo Avenue Storm sewer replacement from Monroe Street to Keeney Street | The project was identified in the 2018 Stormwater Master Plan update at a top quartile project. Stormwater Project # 17-26P The project advancement was recommended by the Stormwater commission | The project will reduce flooding on Oketo Avenue. The project is an extension of the Cleveland Sewer | Project will likely result in a reduction in the amount of calls for service on Oketo Avenue; Grant dependent project FY24 $650,000 Construction cost Previous costs: $55,050 Engineering Design | 2 |  |  | 55050 | 650000 |  | 650000 |  |  |  |  | 0 | [5 empty] | 405050 |  |  |  |  | 300000 | 705050
PW | 25 | Infrastructure Planning and Funding | Blank | Project | Pavement Rehabilitation Senior Center (many times delayed - seven years) | Rehabilitation of the Senior Center Parking Lot | The senior center parking lot is at the end of its useful life and needs major maintenance and rehabilitation. The Senior Center Parking lot is also the venue for various Civic events such as the Holly Jolly festival. The deterioration of the lot has also resulted in workers compensation claims. | The project will improve aesthetics to support economic development and beautify the Village. | The lot should be resurfaced on an approximately 15 year schedule. The 2021 estimated cost for this work is $200,000 | 1 |  |  |  | 200000 | 200000 | [5 empty] | 200000 | 200000 | [10 empty] | 200000
PW | 26 | Infrastructure Planning and Funding | Blank | Project | Touhy Avenue Gap Lighting Franks Ave to Milwaukee Ave. (combine with proj 16) | The Gross Point and Touhy Intersection improvement includes new lighting up to the Chicago River Bridge. This project provides lighting for the gap between Franks and Milwaukee | As part of either the Touhy Bridge replacement or the intersection improvement, IDOT will require ComEd to take take down the existing Touhy Avenue Street lighting since it does meet current design standards. This project will allow for uniform corridor lighting from Milwaukee Avenue to Caldwell | The project will improve aesthetics to support redevelopment and beautify the Village. The project maintains and improves the current level service. | There will be minor addition to electricity costs FY23 $160,000 Design and Construction cost | 1 |  |  |  | 160000 | 160000 | [5 empty] | 160000 | 160000 | [10 empty] | 160000
PW | 27 | Infrastructure Planning and Funding | Blank | Project | Annual Street Improvement Program Beginning FY26 | Pavement Rehabilitation Project | The streets are as identified in the 2018 State of the Street Report. The State of the streets report will be updated prior to FY26 and the recommended funding level will be adjusted at that time. | The $2,700,000 annual funding rate is expected to be sufficient to maintain our average PCI after the larger bond project. This dollar value is based on the 2018 state of the street report. The State of the streets report will be updated prior to FY26 and the recommended funding level will be adjusted at that time. | $2,700,000 year | 1 |  |  |  | 5400000 |  |  |  | 2700000 | 2700000 |  | 0 | [9 empty] | 5400000 |  | 5400000
PW | 28 | Infrastructure Planning and Funding | Blank | Project | FY23-25 Street Improvement Program | Pavement Rehabilitation Project | The streets are as identified in the 2018 State of the Street Report. | The Goal is to achieve an average Village Pavement Condition Index rating of 65. The expenditure of these funds will save many streets from more costly future maintenance and rehabilitation | Debt service payments to be calculated by Finance | 1 |  |  |  | 18700000 | 4600000 | 7050000 | 7050000 |  |  |  | 0 | [9 empty] | 18700000 |  | 18700000
PW | 29 | Infrastructure Planning and Funding | Foster Community Identity | Project | Touhy Avenue Banner sign and monuments | Niles branded sign across Touhy Avenue at the Chicago River. Decorative Monument lights at Touhy Avenue Bridge. | The existing Chicago River Bridges in town are very under stated and are not celebrated. The elected officials have requested a banner sign and monument piers (similar to Howard for the Touhy Bridge approaches) | The project will improve aesthetics to support redevelopment and beautify the Village. | There will be minor addition electricity costs FY24 $300,000 Construction cost | 2 | x |  |  | 300000 |  | 300000 |  |  |  |  | 300000 | 300000 | [10 empty] | 300000
PW | 30 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Milwaukee Avenue Streetscape Phase V | Streetscape improvements from Monroe to Greenwood | The Milwaukee Corridor committee recommended the proposed design as part of their normal agenda process. The schedule is dependent on receiving ITEP funds. | The project will improve aesthetics to support redevelopment and beautify the Village. | There will be added maintenance costs for landscape brick pavers, street furniture, pedestrian lights, and irrigation systems; grant dependent Project funding ratio is 80% federal/20% local | 3 |  |  |  | 4500000 | 4500000 | [5 empty] | 0 |  |  | 900000 | [7 empty] | 3600000 | 4500000
PW | 31 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Milwaukee Avenue Streetscape Phase VII | Streetscape improvements at Milwaukee and Waukegan; and Oakton and Waukegan | The Milwaukee Corridor committee recommended the proposed design as part of their normal agenda process. The schedule is dependent on receiving ITEP funds. | The project will improve aesthetics to support redevelopment and beautify the Village. | There will be added maintenance costs for landscape brick pavers, street furniture, pedestrian lights, and irrigation systems; grant dependent Project funding ratio is 80% federal/20% local | 3 |  |  |  | 1250000 | 1250000 | [5 empty] | 0 |  |  | 250000 | [7 empty] | 1000000 | 1250000
PW | 32 | Infrastructure Planning and Funding | Foster Community Identity | Project | Village Hall Campus Redesign |  | The failing infrastructure, outdated aesthetics and lack of civic building pride is in need of a complete face-lift. |  | Project needs more details to develop funding plan | 1 | x |  |  | 3000000 | 250000 | 2750000 |  |  |  |  | 250000 | 3000000 | [9 empty] | 1800000 | 4800000
PW | 33 | Infrastructure Planning and Funding | Blank | Project | Above Ground Mobile Truck Lifts | (6) Mobile Column Lifts are required to safely lift a wide range of heavy duty vehicles quickly and efficiently. From water sewer vans and pumper trucks to PACE buses and Tower trucks, these mobiles lifts can safely handle them all. Lifting capacities of 18,500lbs. per column can handle any vehicle that the Village owns | Our existing lifts are obsolete and cannot safely lift modern heavy duty vehicles. | Decreased potential workman's compensation claims by keeping staff off of their backs and safely elevating the trucks to a proper working height. This is also a far cheaper alternative with less environmental impact than replacing with in-ground hydraulic truck lifts |  | 2 |  |  |  | 80000 | 80000 | [5 empty] | 0 | [6 empty] | 80000 |  |  |  |  | 80000
FC | 34 | Infrastructure Planning and Funding | Blank | Maintenance | Replacement of Front Lobby Doors Interior and Exterior | The Front Lobby doors of Fitness Center interior/exterior will be replaced. Type of replacement will be considered by evaluation/quoted fee from vendor | The Front Lobby doors are original to the building and have reached their life expectancy. They are both a safety and an environmental concern. The front area of the fitness center creates a wind tunnel and during extreme weather conditions the both exterior/interior does do not shut properly. People entering/existing the building are not able to open the doors properly creating a potential for injury. In addiction due to these doors not closing properly the controlling the heating and cooling of this area is extremely difficult. | Replacement of Front Lobby Doors will address both the safety and environmental concerns of the lobby area. The planning/timing of this project will need to take place during the warmer months. Involvement of IT and PW will need to take place in assisting of security and possibility of re-locating entering/exiting of facility as this is the fitness center's main entrance. | The Front Lobby Doors will be under a warranty for a period of time. therefore service calls to vendors and calls into PW for assistance will be greatly reduced. IT will need be involved in the beginning of this project to make sure that the replacement doors will work within the existing fitness center security system which involves the scheduling of opening/closing the building entrances/exits | 2 |  |  |  | 50000 |  | 50000 |  |  |  |  | 0 |  | 50000 | [9 empty] | 50000
FC | 35 | Infrastructure Planning and Funding | Blank | Maintenance | Replacement of Flooring in Cardio/Weight Area of the Fitness Center | The carpet and mondo flooring in Cardio/Weight Area of the Fitness Center will be replaced Type of flooring replacement and configuration will be considered by vendor's evaluation/quoted fee | Cardio/Weight Area flooring is original and has experienced an extreme amount of wear and tear. This includes not only foot traffic but of bodily fluids from sweating. We are limited to how much cleaning of the carpet can be done without creating more wear and tear to this area. In addition we are seeing a need for less carpet and more mondo flooring to expand the weight area (member requests) and ease of keeping clean | Replacement and reconfiguration of the carpet/mondo flooring will allow for expansion of the weight area. This is a request from not only our current membership base but the future of fitness workout. We believe this re-configuration of the fitness room will attract a younger membership base. While we acknowledge increasing the weight area will decrease the cardio area, this will allow fitness staff to evaluate the use of cardio equipment, such as not repairing equipment (expense) that is end of life and not being used by members (waste of floor space) | Previous expenses : In-house such as cleaning and minor repairs to the carpet area. Professionally cleaned yearly $250.00 This project will reflect a positive impact on entering the Cardio/Weight Area and allow for a better work out configuration for new and existing members. | 2 |  |  |  | 56550 |  | 56550 |  |  |  |  | 0 |  | 56550 | [9 empty] | 56550
FC | 36 | Infrastructure Planning and Funding | Blank | Maintenance | Re-Support of Pool Duct Work To Beams | Labor, materials,and lift needed to install additional trapeze for all duct work hanging over pool area (Please see additional quote information attached to the profile) | On May 26, 2021 staff from the Niles Family Fitness Center (NFFC), Public Works (PW), Community Development (CD) and the Acting Village Manager walked through the NFFC facility. This exercise was conducted in reaction to a failure of a lighting fixture above the NFFC pool in February 2021. 1. Concerns were raised that the HVAC above the pool was corroding and risked potentially falling. During the annual August pool draining, NFFC staff should have a company secure HVAC above the pool. (This was discussed and place on hold until the FY 23 Budget) | This project was placed on hold until it could be placed in the FY 23 Budget under capital improvements. It would be completed as a safety enhancement to the pool area. | It would be a one time expense. This is a non-revenue producing project(please see attached quote for expenses) | 2 |  |  |  | 21980 | 21980 | [5 empty] | 0 |  | 21980 | [9 empty] | 21980
FC | 37 | Infrastructure Planning and Funding | Blank | Maintenance | Fitness Center HVAC Gym Roof Top Units (RTU) | Replacement of two existing Gym HVAC RTU | These are the last two original units to be replaced. They are currently over 20 years old and have met their life expectancy Currently the fitness center has no back up Gym HVAC RTUs that can be used during extreme weather conditions where temperatures fluctuate or in the case of RTU failure. The gymnasium is a multi use fitness area that requires quality air circulation and temperature control | With the addition of (2) HVAC gym roof top units the Fitness Center will have a fully functioning HVAC system. This will allow those members and guests utilizing the gymnasium, track, open basketball, and group fitness classes to work out in well circulated temperature controlled environment | In 2020 (2) HVAC Roof Tops units were replaced for a cost of $120,000 funded by CIP. These two Gym RTUs are under warranty until 2025 and have incurred no maintenance costs Annual estimated maintenance expenses for the remaining two gym roof top units for this year has been approximately $5,000 Their will be no maintenance expenses with new RTUs as they will be under a five year warranty | 2 |  |  |  | 120000 |  | 120000 |  |  |  |  | 0 |  | 120000 | [9 empty] | 120000
FC | 38 | Infrastructure Planning and Funding | Blank | Maintenance | Membership Service Desk (Front Desk)-Remodel | The Membership Service Desk (Front Desk) will be remodeled Type of remodeling will be considered by vendor evaluation/quoted fee | The Membership Service Desk (Front Desk) is original to the building and has experienced wear and tear as this is the focal point of all business conducted by the fitness center (please see pictures attached). If the Front Lobby Door Replacement were to be approved this would be an optimal time to upgrade the Membership Service Desk (Front Desk). | Remodeling of the Membership Service Desk(Front Desk) area will give an aesthetically pleasing visual as people enter and exist the Fitness Center. This area is not only used by Fitness Center's members and guests but is also used by people making there way to and from the Senior Center and Family Services. In future planning discussions it has been suggested that the Fitness Center Lounge Area host the Arts Council Special Events. If that were to take place the main lobby of the Fitness Center would need to be visually appealing to all those entering. As we are all aware first impressions are lasting impressions. Involvement of IT/PW will need to take place in assisting of moving of computers and the possibility of re-locating the Membership Service Desk (Front Desk) | Previous expenses we done in-house and were general and minor repairs to shelving an cabinetry. This project will not be revenue producing and expenses are minor. The project will reflect a positive impact on entering the Fitness Center as well as other areas of the building | 2 |  |  |  | 9700 |  | 9700 |  |  |  |  | 0 |  | 9700 | [9 empty] | 9700
PW | 39 | Infrastructure Planning and Funding | Blank | Maintenance | Fire hydrant flushing and testing program | Flush and test all Village fire hydrants. | Fire hydrant testing is very important to the Village of Niles. Hydrants should be tested and inspected at least annually. Hydrant maintenance and upkeep is one of many steps to keeping the Village's Insurance Service Office (ISO) certification low. ISO developed ratings for fire departments and municipalities. The ratings calculate how well equipped fire departments are to put out fires in that community. The ISO provides this score to homeowners insurance companies, which helps determines homeowner’s insurance rates. A higher ISO score results in lower insurance rates. | Find fire hydrants that are inoperable during the annual testing and repair or replace them. A higher ISO score for the Village. | Provides necessary information of the Village’s distribution system and increases the safety of the residents and businesses in Niles. | 1 |  |  |  | 354000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 354000 | [10 empty] | 354000
FD | 40 | Infrastructure Planning and Funding | Blank | Maintenance | Concrete Driveway Repair | The existing concrete driveway at Fire Station 2 is failing where the fire apparatus regularly drive through. This includes the front entrance to the fire station. | This is both a cosmetic and a safety concern. Visitors to the fire station regularly trip over the holes and gaps created by the failing concrete. In addition, the driveway needs to safely hold the weight of the fire apparatus as they return to quarters. The Tower Ladder needs stable ground to support the outriggers during daily and weekly aerial checks and an unstable driveway poses a safety risk for operations. | Replacing specific failing sections of the concrete driveway will improve safety for fire station 2. It will maintain a safe surface for fire apparatus to drive on, while returning to quarters. It will also eliminate the tripping hazards that currently exist for visitors to the fire station. |  | 2 |  |  |  | 0 | tbd | tbd | tbd | tbd | tbd | tbd | 0 | 0 | [10 empty] | 0
PW | 41 | Infrastructure Planning and Funding | Blank | Maintenance | Crack Sealing | Crack sealing roads to prevent water infiltration. | This work extends the life of the asphalt by preventing water from entering cracks, freezing and damaging the asphalt when it expands. | Crack sealing extends the life of recently paved roadways. The life of your asphalt hinges on asphalt maintenance, so getting an asphalt sealing to combat the cracks is crucial. Asphalt surfaces are compromised by cold weather, extended exposure to UV rays, rain and other elements: asphalt pavement can become brittle and bleached of essential oils over time and begin to crack. When a crack opens up, it is absolutely critical to close it with crack sealants to prevent water from leeching in below the pavement surface. Water is your worst enemy, because it freezes, expands, then thaws and repeats, exacting a toll on your sub base and exponentially worsening existing damage. | Reduction in damage to roadways. With proper maintenance the roads will be safer for pedestrians and vehicular traffic. Life of roads will be extended lessoning the cost of street replacement. | 2 |  |  |  | 900000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 900000 | [10 empty] | 900000
PW | 42 | Infrastructure Planning and Funding | Blank | Maintenance | Pump Replacement: #2 and Pump # 4; add VFD's. | Replacement of Pump #2 and installation of a new VFD on pump #4 at the Touhy Avenue Pump Station. | Pump #2 and Pump #4 has reached its life expectancy and is recommended for replacement. In addition, variable frequency drives (VFD) will be installed to Pump #2 and #4. This will provide substantial energy savings and reduce wear and tear to the motor and pumps. This a recommendation from the Water master plan. | The biggest benefit in replacement of the motors and pumps and installing VFD's is energy cost. VFD’s are used for adjusting flow and pressure to actual demand. It controls the frequency of the electrical power supplied to a pump, thus saving significant power energy. By replacing these pumps and motors, a reduction in electrical usage of approximately 4 percent for each pump could be seen. | The previous funding for replacement of motors and pumps and installing VFD's was $180,000. Staff is anticipating a thirty-percent increase for materials. Future Funding: Staff plans on replacing three more pumps and motor and install VFD's within the next two years. The estimated cost for this is $350,000. | 2 |  |  |  | 234000 | 234000 | [5 empty] | 0 | [5 empty] | 234000 | [5 empty] | 234000
PW | 43 | Infrastructure Planning and Funding | Diversified Economic Development | Maintenance | Tree Planting | Planting trees along village parkways and properties. | The Village of Niles is a Tree City USA. Tree City USA status in critical for funding and grant applications. | Trees combat climate change, help reduce storm water runoff, prevent soil erosion, tree reduce violence, produce economic opportunities, add protection for pedestrians from vehicular traffic. | Trees require maintenance. In order to invent in the growth of Niles and green infrastructure Niles will need to commit funding to maintain village trees. | 2 |  |  |  | 330000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 330000 | [10 empty] | 330000
PW | 44 | Infrastructure Planning and Funding | Blank | Maintenance | Minor Asphalt Repairs | Repairs of large section of roadways. | This work is done in areas where asphalt repairs are needed, but resurfacing is not scheduled within the next five years. Locations are determined on an as needed basis. | The village benefits from this maintenance because it can delay street resurfacing until the entire street needs it. Some repairs are to great for simply filling pot holes. A large section can be completed for a better cleaner looking repair. | With proper maintenance the roads will be safer for pedestrians and vehicular traffic. Life of roads will be extended and delay street replacement. Reduction in overtime for filling potholes. Reduction in injuries to pedestrians from stepping in cracked and broken roadways. | 2 |  |  |  | 480000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 480000 | [10 empty] | 480000
PW | 45 | Infrastructure Planning and Funding | Blank | Maintenance | Traffic Signal Maintenance | Traffic signal maintenance of intersection in the Village of Niles. | The village is required to make sure village owned traffic signals are maintained. This is completed sole source / contract with Meade. | Making sure our traffic signals are working property helps to insure even traffic flow and helps to keep drivers and pedestrians safe while traveling. | Reduction in accident claims. | 2 |  |  |  | 322731.36 | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 322731.36 | [10 empty] | 322731.36
PW | 46 | Infrastructure Planning and Funding | Blank | Maintenance | Tree Trimming | Tree Trimming along village owned parkways and properties. | The Village of Niles is a Tree City USA and allocates money for tree trimming. Tree trimming is critical for the growth of trees and for safety. Trees on the Village of Niles are separated in to five trim zones. One trim zone is completed each year. | Proper trimming improves tree health by eliminating dead or dying branches, trimming improves the overall appearance and structure of the tree, which prevents the development of broad or weak branches. It also keeps limbs from growing with weak crotches, or even crossing each other and competing for space in the crown. Tree trimming also helps to reduce storm damage. | Trees require maintenance and trimming reducing call outs for storm damage, hangers, damage to property and most of all reduces the danger to life. | 2 |  |  |  | 510000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 510000 | [10 empty] | 510000
PW | 47 | Infrastructure Planning and Funding | Blank | Maintenance | Tree Removal | Tree Removal along village owned parkways and properties. | The removal of trees that are dead, diseased or dangerous is necessary to safeguard the lives of Niles residents. It can be equally important to remove trees with diseases to stop the potential spread. | Removing trees that are dead, diseased or dangerous is necessary to safeguard the lives of Niles residents. Removal of trees that can posses hazards lowers claims of injuries and property damage. Trees that fail can cause power outages which impacts residents who survival depends on electricity. | Removal of these trees reduces call outs for storm damage, hangers, damage to property and most of all reduces the danger to life. Insurance claims are lower and phone calls to the department for service are reduced. | 2 |  |  |  | 510000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 510000 | [10 empty] | 510000
PW | 48 | Infrastructure Planning and Funding | Blank | Maintenance | Sewer Cleaning and Televising Program | The sewer cleaning and televising program is to clean debris from both sanitary and storm lines and find deficiencies. | The purpose of this work is to clean debris from both sanitary and storm lines. After cleaning, internal closed circuit television is used to inspect sewers and identify structural defects, misalignments, service lateral connections and deficiencies. | The sewer cleaning and televising program provides necessary information related to the Village’s sewer system and provides better operation of the sewer system. | Identify the scope of the repairs necessary, including sewer lining, spot repairs or complete pipe section excavation and replacement. | 2 |  |  |  | 510000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 0 | [5 empty] | 510000 | [5 empty] | 510000
PW | 49 | Infrastructure Planning and Funding | Blank | Maintenance | Sewer Lining Program | CIPP is designed to restore our sewer lines to proper operating conditions. | Cured-in-place pipe (CIPP) is a trenchless rehabilitation method used to repair existing sewer pipes. CIPP is a jointless, seamless, pipe-within-a-pipe with the capability to rehabilitate sewer pipes and restore structural integrity. | One of the greatest benefits of sewer lining is there is no road construction and minimal disturbance to our residents. There is also a fifty-year design life, the same as that of a new pipe. | CIPP sewer lines that are deteriorating. | 2 |  |  |  | 1500000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 0 | [5 empty] | 1500000 | [5 empty] | 1500000
PW | 50 | Infrastructure Planning and Funding | Blank | Maintenance | Water main Valve Exercising Program | To ensure that water valves can be located efficiently and closed to isolate part of the water system in case of an emergency, water main breaks or repair. | This program verifies that the valves are in the correct operating position so as to maximize flow and pressure for firefighting and normal operation. The American Water Works Association (AWWA) recommends that each valve should be operated yearly. | Valve exercising is designed to prevent buildup/scaling on the inside of the valve which could cause the valve to be inoperable. This is done multiple times until the valve opens and closes smoothly. After the valve is exercised, the contractor documents the location of the valve, condition and if any maintenance is needed. | Repair inoperable valves when found to ensure the water system is working properly. | 2 |  |  |  | 492000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | 492000 | [10 empty] | 492000
PW | 51 | Infrastructure Planning and Funding | Blank | Project | Greenleaf Sewer Rehabilitation | Sanitary sewer repair and lining for Greenleaf sewer in Chesterfield Gardens | The project was identified through the Public Works televising program as a sewer in need of major maintenance and repair. | The project will reduce sewer backups in Chesterfield Gardens. | Project will result in a reduction in the amount of calls for service for sewer cleaning to the Chesterfield Gardens. FY23 $167,000 Construction and construction engineering cost Previous costs: $21,436 Engineering Design | 1 |  |  | 21436 | 167000 | 167000 | [5 empty] | 167000 | 188436 | [10 empty] | 188436
PW | 52 | Infrastructure Planning and Funding | Diversified Economic Development | Project | Melvina Street Rehabilitation | Pavement Rehabilitation Project from Touhy to Gross Point. Watermain replacement, lighting, and bike improvements. FY 24 project | The street is identified as needing repair in the 2018 State of the Streets Report. The Water system master plan identifies the watermain as a high priority for replacement. | The project will increase fire flows to support redevelopment in the area. A revitalized Melvina Avenue will also help encourage redevelopment within the Triangle. Replacing the roadway before the PCI gets too low will reduce the scope of work and cost. | $0 - This is TIF funded so operation should not be affected Previous expenditure ($297,810 Design Engineering) | 1 |  |  | 297810 | 2600000 |  | 2600000 |  |  |  |  | 0 |  |  |  |  | 2897810 | [6 empty] | 2897810
PW | 53 | Infrastructure Planning and Funding | Blank | Maintenance | Milwaukee Brick Crosswalk Replacement | Replacement of Decorative Milwaukee Crosswalks with Thermoplastic Crosswalks | The Milwaukee Corridor committee selected decorative Thermoplastic Crosswalks for the replacement of the poor performing Brick paver crosswalks. The cross walks have been replaced incrementally on an annual basis. | The project will improve aesthetics to support redevelopment in the area. The existing crosswalks are also settling and deteriorating resulting in a driving hazard. The hazard will be removed. | The cross walks will need to be replaced every 10-years or so. Replacement costs will be much less than the initial cost since much of the initial cost is related to removal of the brick paver walk. FY23 $250,000; FY 24 $25,000 design; FY 25 $250,000, FY26 $25,000 design, FY27 $250,000 | 2 |  |  |  | 800000 | 250000 | 25000 | 250000 | 25000 | 250000 |  | 250000 | 800000 | [10 empty] | 800000
PW | 55 | Infrastructure Planning and Funding | Blank | Maintenance | Lower Level Mechanical Roof, Chiller and Access Door | Replacement of the Lower Level Mechanical Roof, Chiller Unit and Access Door at Village Hall | The Lower Level Mechanical Roof has surpassed its 25 year life expectancy and is in need of full replacement. This area was not address when the roof was previously refurbished and has failed. Failure to replace the roofing system will result in damages caused by water intrusion and will continue to the damage the infrastructure prematurely. Furthermore, the Chiller unit located on the mechanical roof is original to the building, nearly obsolete, and should be replaced at the time of removal | Best practice roofing management will extend the life of the building and eliminate water intrusion |  | 2 |  |  |  | 270000 | 270000 | [5 empty] | 270000 | 270000 | [10 empty] | 270000
PW | 56 | Infrastructure Planning and Funding | Blank | Maintenance | Replacement of Exterior Door and Frames at 1000 Civic Center Drive | Demolition and replacement of 12 exterior doors and framework 1000 Civic Center Drive | The exterior doors and framework are badly corroded, potentially unsecure, and have past their life expectancy. | Increased security, improved aesthetic, improved envelope protection from weather. |  | 1 |  |  |  | 108000 | 108000 | [5 empty] | 108000 | 108000 | [10 empty] | 108000
PW | 58 | Infrastructure Planning and Funding | Blank | Maintenance | HVAC Replacements at PW Campus | Replacements of Above ceiling Computer Room Unit remote condenser serving Server Rooms | The aforementioned HVAC units have surpassed their life expectancy or are entirely obsolete and require replacement. | Being that the project is multi-tiered, workload permitting, Facilities staff can be utilized to reduce costs by purchasing individual units and installing in-house |  | 2 |  |  |  | 50000 | 50000 | [5 empty] | 50000 | 50000 | [10 empty] | 50000
PW | 59 | Infrastructure Planning and Funding | Blank | Maintenance | HVAC Replacements at 7000 W. Touhy | Rooftop Unit RTU-1 serving Jail Cells,Rooftop Unit RTU-3 serving Lower Level Locker Rooms,Rooftop Unit, Rooftop Unit RTU-6 serving the Second Floor Offices, Add Mini-Split System to Fingerprint Area,Computer Room Unit CRIU-3 ducted cooling unit and remote condenser serving Lower Level Electrical Room | The aforementioned HVAC units have surpassed their life expectancy or are entirely obsolete and require replacement. | Being that the project is multi-tiered, workload permitting, Facilities staff can be utilized to reduce costs by purchasing individual units and installing in-house |  | 2 |  |  |  | 300000 | 300000 | [5 empty] | 300000 | 300000 | [10 empty] | 300000
PW | 60 | Infrastructure Planning and Funding | Blank | Maintenance | HVAC Replacements Shared Units for Senior Center and Family Services | Hot Water Pumps serving entire building AHU-1 serving Senior Center & Family Services AHU-1 Variable Frequency Drives serving Senior Center & Family Services Wood gas piping supports on roof are deteriorated. Trane Temperature Controls serving building are obsolete | Multiple components of the HVAC system at 999 Civic Center Drive (The Senior Center, Health and Wellness )has surpassed its 25 year life expectancy and is in need of full replacement. Components are beyond repair, have exceeded their life expectancy and or are obsolete. | Reduced maintenance costs, replacements will be serviceable and have a live of over 20 years |  | 2 |  |  |  | 725000 | 725000 | [5 empty] | 725000 | 725000 | [10 empty] | 725000
PW | 61 | Infrastructure Planning and Funding | Blank | Maintenance | Repair/Replacement of Exterior Walls,Gutters and Soffits at 999 Civic Center Drive | An exterior refresh of 999 Civic Center Drive is needed to assure the building envelope health. Tuckpointing, and cleaning of the brickwork is required in various areas of the building, the gutters and downspouts are in need of replacement, along with the water damaged soffit overhang in the rear of the building. | The exterior masonry, gutter system, and soffit overhang system at 999 Civic Center Drive are in disrepair and need immediate attention . Failure to replace or repair the the building envelope will result in damages caused by water intrusion and will continue to the damage the infrastructure prematurely. | Best practice roofing management will extend the life of the building and eliminate water intrusion |  | 2 |  |  |  | 250000 | 250000 | [5 empty] | 250000 | 250000 | [10 empty] | 250000
PW | 62 | Infrastructure Planning and Funding | Blank | Maintenance | Truck Wash Restoration | Reconfigure and plumb undercarriage wash, repair drainage, and reseal repaired concrete. | The undercarriage wash is in disrepair and requires plumbing upgrades and photo-eye activation. Additionally, the newly repaired concrete must be sealed in order to sustain its life expectancy. | Repairing the undercarriage wash will extend the life of our fleet's frame components, lowering maintenance costs and raising the likelihood of a high ROI when the vehicles are sold. Additional, the wash bay floors life will be extended and improver worker safety |  | 2 |  |  |  | 90000 | 90000 | [5 empty] | 90000 | 90000 | [10 empty] | 90000
PW | 63 | Infrastructure Planning and Funding | Blank | Maintenance | Full roof restoration at 7000 W. Touhy | Repair Adverse Membrane Conditions Present. Removal of Areas of Wet Insulation. Installation of New Perimeter and Penetration Flashings. Thorough Cleaning of Existing Membrane Surfaces. Application of New Restoration Treatment at Rates Specified. Application of New Surfacing Option | The roof system is original from the time the building was constructed in the early 2000s. Since the time of construction, the station has been experiencing severe leak issues in the main lobby area. It appears as though there are some drainage design issues, as well as, a composite wall paneling system that could have been improperly installed and experiencing saturation and deterioration. Failure to restore the roofing system will result in damages caused by water intrusion and will continue to the weaken the infrastructure prematurely. | A restoration of an existing roof is a lower cost alternate to full replacement estimated at $1,200,000. A restoration can extended the life of the existing roof system by 20-40 years (Fluid applied membrane can be applied more than once). |  | 2 |  |  |  | 310000 | 310000 | [5 empty] | 310000 | 310000 | [10 empty] | 310000
PW | 65 | Infrastructure Planning and Funding | Blank | Maintenance | Replacement of Exterior Door and Frames at PD Campus | Demolition and replacement of 5 exterior doors and framework of the PD Campus | The exterior doors and framework are badly corroded, potentially unsecure, and have past their life expectancy. | Increased security, improved aesthetic, improved envelope protection from weather. |  | 2 |  |  |  | 45000 | 45000 | [5 empty] | 45000 | 45000 | [10 empty] | 45000
PW | 66 | Infrastructure Planning and Funding | Blank | Maintenance | Replacement of Exterior Door and Frames at PW Campus | Demolition and replacement of 21 exterior doors and framework of the PW Campus | The exterior doors and framework are badly corroded, potentially unsecure, and have past their life expectancy. | Increased security, improved aesthetic, improved envelope protection from weather. |  | 2 |  |  |  | 170000 | 170000 | [5 empty] | 170000 | 170000 | [10 empty] | 170000
IT | 67 | Marketing and Communication | Blank | IT/Purchase | Audio Visual and Conference Room Improvements | A/V and conferencing systems update/refresh. | The current systems do not meet the user community demands to aid in collaboration and multimedia presentations. Many of our current A/V and conferencing systems at the Village Hall (Council Chambers, 1st and 2nd Floor conference rooms), Police Station (training room), Fitness Center, and Family Services (Multi-Purpose rooms) must be refreshed as they have gone past their useful life. | Improve collaboration and more productive meetings and presentations without being challenged due to outdated systems. | Negligible under 4% | 2 |  |  |  | 28000 | 28000 | [5 empty] | 28000 | 28000 | [10 empty] | 28000
IT | 68 | Infrastructure Planning and Funding | Blank | IT/Purchase | End-User Device Refresh Lifecycle | Refresh end-user desktops at the end of life 4~5 year cycle at the rate of 50 desktops a year. -This will include desktop or laptop and typical peripherals such as scanners, webcams, headsets, monitors, docking stations, software licenses, including end-point protection, i.e., antivirus and malware protection. | The village needs to be on a regular end-user device refresh life cycle to maintain its fleet of computers functional and in operating conditions. | Maintain efficient day-to-day operations of the Village administration and management. | $70,000. annual | 2 |  |  |  | 70000 | 70000 | [5 empty] | 70000 | 70000 | [10 empty] | 70000
IT | 69 | Infrastructure Planning and Funding | Blank | IT/Purchase | IT Infrastructure Improvements | Network and Wifi remedation | The Village's IT Network and WiFi infrastructure have been plagued with network outages that have crippled the staff's ability to utilize the IT network and Internet Services. Network remediation will address network availability and reliability. | Reliable Internet and network communications between and within the Village sites for all staff and guest users; | none *the operating maintenance budget will be realigned and offset existing costs. | 2 |  |  |  | 98000 | 98000 | [5 empty] | 98000 | 98000 | [10 empty] | 98000
IT | 70 | Infrastructure Planning and Funding | Blank | IT/Purchase | O365/M365 Migration | Office 365 migration | Currently, the Village hosts many Microsoft Enterprise services on-premises that have been less and less reliable and require a more advanced skill set to administer, manage, and current. The on-premises model has become unsustainable and is plagued with system outages. | Improve system and service availability and reliability for all stakeholders. By migrating to Office 365, the IT department will be better positioned to deliver IT services to Citizens, Staff, and businesses. Also, it would enhance our system uptime and security. | In the short run, as we migrate, there will be a nominal increase, but after a year, we will rebalance as we remove our technology debt and decommission systems. | 2 |  |  |  | 92600 | 92600 | [5 empty] | 92600 | 92600 | [10 empty] | 92600
IT | 71 | Infrastructure Planning and Funding | Blank | IT/Purchase | SCADA Security | Secure the Village's Supervisory control and data acquisition (SCADA) system. SCADA is a system of software and hardware elements that enables the Water Department to control industrial processes locally or at remote locations; Monitor, gather, and process real-time data; Directly interact with devices such as sensors, valves, pumps, motors, and more through human-machine interface (HMI) software; Record events into a log file; | The Village's SCADA system is vitally important tool for operating, managing, and monitoring public water. SCADA now has an ever-present role that includes looking after all automatic control and alarm management, logging of critical process data, and providing operators with remote access to equipment. In recent months the SCADA systems have been targets of cyber and ransomware attacks, it is more important than every to secure the SCADA system with network air-gap methodology. | Securing the Village's critical infrastructure Water Supply Plant from cyberattacks by minimizing vulnerabilities. | Less than 4% annual. | 2 |  |  |  | 36000 | 36000 | [5 empty] | 36000 | 36000 | [10 empty] | 36000
FD | 72 | Infrastructure Planning and Funding | Blank | IT/Purchase | Purchase New Ambulance | Replace heavily used and worn out ambulance from 2009. A new ambulance will allow for a reliable vehicle to respond to medical emergencies without delay. | This ambulance will replace an aging ambulance that is worn out and encountering increased annual maintenance costs. The ambulance being replaced is over ten years old. The fire department standard is to operate an ambulance five years in front line status and five years in backup status. | A newer ambulance provides improved comfort and reliability for those being transported. It will reduce annual maintenance costs. It will allow operations at the current modern standard of medical care. |  | 2 |  |  |  | 325000 |  | 325000 |  |  |  |  | 0 | [6 empty] | 325000 |  |  |  |  | 325000
FD | 73 | Infrastructure Planning and Funding | Blank | IT/Purchase | Purchase New Fire Engine | Replacement of aging and deteriorating 1992 fire engine. | The existing engine is very old, rusted and struggles with maintenance repairs. Parts are being difficult to find for this vehicle. | Having a reliable fire apparatus will allow the fire department to effectively maintain its operations. |  | 2 |  |  |  | 875000 |  | 875000 |  |  |  |  | 0 | [6 empty] | 875000 |  |  |  |  | 875000
PW | 74 | Infrastructure Planning and Funding | Blank | IT/Purchase | Replace (11) Civic Center Vehicles with (8) Electric "Motor Pool" Vehicles | Replace (11) General Government Vehicles, (10) 2007 Ford Fusions and (1) 2000 Crown Victoria with (8) Electric "Motor Pool" Vehicles. This project will also include charges that will be installed by the Village Electrician. | Replace (11) General Government Vehicles, (10) 2007 Ford Fusions and (1) 2000 Crown Victoria with (8) Electric "Motor Pool" Vehicles. This project will also include charges that will be installed by the Village Electrician. | The General Government and Code vehicles will be stored at Village Hall and are the perfect candidate for an electric fleet. The vehicles are not used for long distances and can be charged over night while parked at Village Hall. |  | 2 |  |  |  | 400000 |  | 400000 |  |  |  |  | 0 | [6 empty] | 400000 |  |  |  |  | 400000
PW | 75 | Infrastructure Planning and Funding | Blank | IT/Purchase | Replace (2) Detective Sedans Units #104 and #107 | Replace (2) 2007 Dodge Charger Sedans with (2) 2023 Police SUV's | The rear wheel drive detective sedans are not well suited for winter service and must be replaced with an all wheel drive vehicle. Furthermore, the vehicles are beyond their service life and have proven to be unreliable for emergency service | Reduced maintenance, increased safety, increased officer ergonomics. |  | 1 |  |  |  | 90000 | 90000 | [5 empty] | 0 | [6 empty] | 90000 |  |  |  |  | 90000
PW | 76 | Infrastructure Planning and Funding | Blank | IT/Purchase | Replace (2) Water Department Trucks Units #440 and #472 | Replace (2) Water Department trucks 2008 and 2006 models with (2) 2023 Utility Body trucks. The replacement vehicles will be built on Ford F-350 Chassis and Knapheide service bodies that will be used by the water department for service calls and for winter snow removal operations. | 440 and 472 are badly corroded, past their service life and require replacement. | Reduced maintenance, increased safety, increased officer ergonomics. |  | 2 |  |  |  | 170000 | 170000 | [5 empty] | 0 | [6 empty] | 170000 |  |  |  |  | 170000
PW | 77 | Infrastructure Planning and Funding | Blank | Project | Build (4) Hooklift attachments for PW Trucks | In lieu of full truck replacements for specialty equipment, 4 Hooklift attachments will be built to serve multiple areas of the Public Works Operation. An asphalt "hot box" body, a Chipper Box, A Watering and De-Icing Tanker and a Flat Bed Trailer | The interchangeable attachments allows us replace only the working components of the truck and not the entire truck itself. The package allows for the working capacity of 4 trucks for the cost of 1. This practice will save the village over $500,000 in truck costs alone. | Reduced maintenance, increased safety, increased officer ergonomics. |  | 1 |  |  |  | 310000 | 310000 | [5 empty] | 0 | [6 empty] | 310000 |  |  |  |  | 310000
PW | 78 | Infrastructure Planning and Funding | Blank | IT/Purchase | Replace Sewer Department Van #478 | Replacement of Water Department Cube Van #478 2008 Chevrolet E3500 Upfit with Morgan Olsen Route Star Walk-In Van body and applicable hardware for water main repairs. | 478 has past its service life and requires replacement. | Reduced maintenance, increased safety, increased ergonomics. |  | 1 |  |  |  | 180000 | 180000 | [5 empty] | 0 | [6 empty] | 180000 |  |  |  |  | 180000
PW | 79 | Infrastructure Planning and Funding | Blank | IT/Purchase | 499 Street Sweeper Replacement | Replacement unit will serve as the primary street sweeper for sweeping and leaf pickup operations | The 14-year-old street sweeper has exceeded its life expectancy and has proven unreliable to the Street Department. 499 has suffered multiple breakdowns that needed costly heavy-duty tows during critical clean-up situations, such as leaf pick up, three times this year. | Reduced maintenance costs, elimination of costly $10,000 winter rebuilds, increased duty cycle, lower carbon footprint by way of increasing fuel efficiency. |  | 1 |  |  |  | 300000 | 300000 | [5 empty] | 0 | [6 empty] | 300000 |  |  |  |  | 300000
IT | 80 | Infrastructure Planning and Funding | Blank | IT/Purchase | End-User Device Refresh - CD | Refresh Community Development Department End-User Devices for Inspectors, and Managers. | Community Development staff utilizes technology to conduct inspections and permitting, the end-user devices for the department needs to be more flexible and mobile. The department is due for refresh of desktop, screens, scanners and printer. | Maintain efficient day-to-day operations of the Community Development functions and management thereof. |  | 2 |  |  |  | 30500 | 28000 | 500 | 500 | 500 | 500 | 500 | 28000 | 30500 | [10 empty] | 30500
PW | 81 | Infrastructure Planning and Funding | Blank | Project | Complete lead service line replacement utilizing IEPA forgivable loans | Complete replacement of lead services lines as part of Lead Service Line Replacement Program | HB-3739 created a statutory requirement for the Village to completely replace lead service lines when they are disturbed. Partial replacement of lead service lines present a public health issue. The Village is working on a lead service line replacement plan which must be completed by 2024. Approximately 4000 lead services in town will need to be replaced over a 17 year period However as an interim policy the lead services that are disturbed after January 1, 2022 must be replaced in full. | The project will eliminate a public health hazard in Niles and improve the marketability of our housing stock.. Utilization of low interest of forgivable IEPA loans presents the lowest cost financing solution to this problem. | The annual cost to our water fund will be in the range of $4,000,000/year however a portion to all of the loan costs will be forgivable. FY23 -FY27$4,000,000, The Village would potentially be required to front the payments and request loan disbursement reimbursement | 1 |  |  |  | 20000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 |  | 0 | [5 empty] | 10000000 |  |  |  |  | 10000000 | 20000000
PW | 82 | Infrastructure Planning and Funding | Blank | Project | Touhy Avenue Watermain Replacement | Touhy Avenue watermain replacement from Caldwell to Lehigh | The 2016 Water System Master Plan specifically recommended the replacement of the Touhy Avenue watermain to improve fire protection service level FY 23 $200,000 for design engineering FY 25 $3,800,00 for construction | The project will reduce water loss, reduce the frequency of water main breaks, improve system reliability, improve valve interoperability, improve water quality, improve fire flow, improve system pressure, and increase the overall value of the water system. | Watermain replacement reduces operational cost related to water loss and emergency watermain break repair. | 1 |  |  |  | 4000000 | 200000 | 3800000 |  |  |  |  | 0 | [5 empty] | 4000000 | [5 empty] | 4000000
PW | 83 | Infrastructure Planning and Funding | Blank | Project | Watermain Replacement Program FY24 - FY27 | Watermain replacement for end of service life watermains | The Matrix study as well as the 2016 Water System Master Plan recommended the replacement of 1.3%-2% per year according to ASCE industry standards. This equates to 1.3-2 miles of watermain replacement per year. The following minimum recommended budget allocation made based on historic program expenditures: FY24 -FY27 $2,000,000/year | The project will reduce water loss, reduce the frequency of water main breaks, improve system reliability, improve valve interoperability, improve water quality, improve fire flow, improve system pressure, and increase the overall value of the water system. | Watermain replacement reduces operational cost related to water loss and emergency watermain break repair. Annual expenditure should be based on the ability to pay for the work as determined as a result of a rate study. | 1 |  |  |  | 8000000 |  | 2000000 | 2000000 | 2000000 | 2000000 |  | 0 | [5 empty] | 8000000 | [5 empty] | 8000000
PW | 84 | Foster Community Identity | Diversified Economic Development | IT/Purchase | Holiday Decorations |  |  |  |  | 2 |  |  |  | 0 | [6 empty] | 0 | [11 empty] | 0
PW | 85 | Infrastructure Planning and Funding | Blank | Maintenance | Post-Bond Street Improvement Maintenance | Funds designated for street maintenance after the 2022 street improvement bond money has been spent. | Over the course of the next 4-5 fiscal years, the PW department will use bond funds to repair streets in an attempt to improve the pavement condition index (PCI) to a level of 65 (see projects #27 and #28). Subsequent to that, staff expect an annual maintenance cost of around $900,000 to maintain that level of pavement condition into the future. |  |  | 1 |  |  |  | 1800000 |  |  |  |  | 900000 | 900000 | 0 |  |  |  | 1800000 | [7 empty] | 1800000
PW | 86 | Infrastructure Planning and Funding | Blank | Maintenance | Employee Parking Lot Gate and Man-Door Replacement | Replace the existing swing gate and man-door with a secure motorized system similar to the Touhy Ave. and Franks Ave. access gates. | The existing gate and man-door that are in place provide no security and are in disrepair. | Increased site security, improved property aesthetic. | Minimal, but aesthetic and security considerations are important. | 2 |  |  |  | 75000 | 75000 | [5 empty] | 75000 | 75000 | [10 empty] | 75000
PW | 87 | Infrastructure Planning and Funding | Blank | Maintenance | HVAC Replacements (IT Room) at 1000 Civic Center Drive. | Replace Liebert units in server room and server room ceiling with modern equipment that is designed to handle additional IT infrastructure. | The aforementioned HVAC units have surpassed their life expectancy or are entirely obsolete and require replacement. | Being that the project is multi-tiered, workload permitting, Facilities staff can be utilized to reduce costs by purchasing individual units and installing in-house. | The project will likely prevent or reduce further emergency maintenance or repairs, likely coming from the General Fund. | 2 |  |  |  | 80000 | 80000 | [5 empty] | 80000 | 80000 | [10 empty] | 80000
PW | 88 | Infrastructure Planning and Funding | Blank | Project | Village Hall Interior Lobby Redesign |  |  |  |  | 1 |  |  |  | 20000 | 20000 | [5 empty] | 20000 | 20000 | [10 empty] | 20000
[13 empty] | 2411447 | 124732187.36 | 25697514.56 | 31700934.56 | 31609684.56 | 10794684.56 | 11919684.56 | 13009684.56 | 7437385.38 | 17452244.18 | 258230 | 5040000 | 3980000 | 2897810 | 38980300 | 2730000 | 0 | 0 | 24100000 | 31517150 | 126955734.18
FitnessProject Costs
Police Memorial/Room Redesign
Auto Fund transfer formula
project tags
Note on A1: Department Abbreviations: Department: PW - Public Works PD - Police FD - Fire FC - Fitness Center SC - Senior Center FS - Family Services CD - Community Development FIN - Finance IT - Information Technology AD - Administration
Note on C1: STRATEGIC PRIORITY AREA: This is define in the Strategic Planning document and consists of one or more of the following: 1) Financial Stability and Transparency; 2) Diversified Economic Development; 3) Marketing and Communication; 4) Infrastructure Planning and Funding; 5) Foster Community Identity.
Note on K1: Schultz, Conor: Tier 1: Must-Have projects to be completed for stability of services Tier 2: Resources (financing and capacity) are available for the designated budget year Tier 3: Stretch goal/Resources Unavailable/Further Clarification Required
Note on M1: Overall Institution Rank.
Note on F3: Schultz, Conor: preexisting plan
Note on J6: Schultz, Conor: additional funds ($35,000+) already in hand?
Note on P8: Schultz, Conor: design engineering
Note on R9: Schultz, Conor: placeholder pending more information
Note on W10: Schultz, Conor: also assignable to the Capital Projetcs Fund or MFT Fund
Note on N11: Schultz, Conor: Engineering Phase 1 and 2 already completed; $30,000 Invest in Cook Grant
Note on O11: Schultz, Conor: Project is programmed for CMAQ ($375,000) and Invest in Cook Funding ($112,500)
Note on W11: Schultz, Conor: Local costs remaining after grants
Note on AG11: Schultz, Conor: $375,000: CMAQ $112,500: Invest in Cook $30,000: Invest in Cook prior spending
Note on P12: Schultz, Conor: design engineering
Note on Q12: Schultz, Conor: construction
Note on W12: Schultz, Conor: could also be Capital or MFT
Note on W13: Schultz, Conor: Niles Share--rest is Morton Grove
Note on AG14: Schultz, Conor: HSIP -$909,000 ITEP- $2,000,000 CMAQ/RTA - $640,000 Local $750,000
Note on N15: Schultz, Conor: warrant study
Note on P15: Schultz, Conor: originally in FY21 budget
Note on W15: Schultz, Conor: Village share
Note on AG15: Schultz, Conor: HSIP, CMAQ, and TAP-L federal funding will be pursued.
Note on F16: Schultz, Conor: potential to split Caldwell into separate project
Note on N16: Schultz, Conor: engineering to date
Note on O16: Schultz, Conor: estimations; see FUND IMPACT
Note on P16: Schultz, Conor: FY 23 budget impact $750,000-$1,500,000
Note on Z16: Schultz, Conor: may change; see comments; federal funding may also be available
Note on S18: Schultz, Conor: Local Match
Note on T18: Schultz, Conor: Local Match
Note on Z18: Schultz, Conor: Historically Niles has funded Phs 1 engineering with MFT funds to improve chances of receiving federal funding in later phases. This project has a high probabilty of obtaining federal funding
Note on AG24: Schultz, Conor: MWRD - Project will pursue $2 million grant from MWRD in CY24 Project is likely eligible an IEPA Low Interest Loan Scope at Harlem eligible for STP and/or IDOT funding
Note on N25: Schultz, Conor: engineering design
Note on AG25: Schultz, Conor: MWRD Grant being sought
Note on F29: Schultz, Conor: Tom has a list of identified roads/projectsfor the first two years of the bond
Note on O29: Schultz, Conor: may be lower, down to $15m
Note on AG33: Schultz, Conor: DCEO application: $1.8m
Note on F35: Schultz, Conor: Talk to Linda/Ernie about cost estimates for these
Note on AA53: Schultz, Conor: G/P Touhy
Note on F89: Schultz, Conor: Cost of construction/renovation outstanding

## Presentation Format
Dept | Proj # | Page # | Category | Project Title | Reason/Description | Fund | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | Finance comments | Department Comments
PW | 33 |  | Project | Above Ground Mobile Truck Lifts | Mobile Column Lifts are required to safely lift a wide range of heavy duty vehicles quickly and efficiently. From water sewer vans and pumper trucks to PACE buses and Tower trucks, these mobiles lifts can safely handle them all. |  | 80000 | 0 | 0 | 0 | 0 | 0
PW | 28 |  | Project | Annual Street Improvement Program (FY23-25) | Pavement Rehabilitation Project |  | 4600000 | 7050000 | 7050000 | 0 | 0 | 0 | This is the project associated with the bond being sought during the current fiscal year (FY22).
PW | 27 |  | Project | Annual Street Improvement Program (FY26-28) | Pavement Rehabilitation Project |  | 0 | 0 | 0 | 2700000 | 2700000 | 0 | This figure represents the annual maintenance costs for maintaining a healthy pavement condition index, beginning in FY26.
PD | 6 |  | Project | Automated License Plate Reader program | This project involves the purchase of 12 Automated license plate reading cameras and updating 2 currently owned ones. The price includes all hardware and software as well as installation. The system will also allow our Axon squad car cameras to function as mobile License plate readers. |  | 38896 | 34396 | 34396 | 34396 | 34396 | 34396
PW | 9 |  | Project | Bike & Ped Update (Project Name/Scope TBD) | A variety of capital projects have been recommended by the BPAG as part of the bike and pedestrian plan update. |  | 50000 | 90000 | 90000 | 90000 | 90000 | 90000 | FY23: $50,000 Design Engineering FY24-27: $450,000 Construction The cost and schedule is dependent on BPAG recommendation and grant funding
PW | 22 |  | Project | Bridge Flag Poles | Installation of Flag Poles at various Chicago River Bridges in Town, including Howard Street, Touhy Avenue, and Hart Road. |  | 40000 | 80000 | 0 | 0 | 0 | 0
PW | 77 |  | Project | Build (4) Hooklift attachments for PW Trucks | In lieu of full truck replacements for specialty equipment, 4 Hooklift attachments will be built to serve multiple areas of the Public Works Operation. An asphalt "hot box" body, a Chipper Box, A Watering and De-Icing Tanker and a Flat Bed Trailer. |  | 310000 | 0 | 0 | 0 | 0 | 0
PW | 21 |  | Project | Caldwell Avenue Niles sign and lighting | Niles branded sign on the Caldwell Avenue Bike Bridge, plus the painting of the bridge, railing rework, and additional lighting. |  | 300000 | 0 | 0 | 0 | 0 | 0
PW | 81 |  | Project | Complete lead service line replacement utilizing IEPA forgivable loans | Complete replacement of lead services lines as part of Lead Service Line Replacement Program |  | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0 | A portion to all of the loan costs will be forgivable. The Village would potentially be required to front the payments and request loan disbursement reimbursement.
FD | 8 |  | Project | Fire Station #2 | This is a multi-phase project to replace the fire station 2 building. This includes feasability analysis to determine building and land needs, architectural design, land acquisition, and construction. |  | 0 | 0 | 14000000 | 0 | 0 | 0 | Project still in initial planning stages.
PW | 13 |  | Project | Golf Road, Milwaukee Avenue, and Greenwood Avenue - Sidewalk Infill | The Village is in the process of designing sidewalk infill from on Golf Road from Dee Road to Washington Road, on Greenwood Avenue from Golf Road to Sunset Road, and Milwaukee Avenue from Golf Road to Maryland Street. |  | 200000 | 750000 | 0 | 0 | 0 | 0 | FY23: $220,000 FY24: TBD Schedule is dependent on IDOT Previous costs: $40,000 for Phs 1 engineering cost share
PW | 19 |  | Project | Green Alley Project | The FY23 budget includes the design of a Green Alley. The Village often pursues green infrastructure grant funding and having a shovel ready project increases the likelihood of receiving funding. |  | 0 | 0 | 600000 | 0 | 0 | 0 | Project will likely result in a reduction in the amount of calls for service received. Permeable pavers would likely result in additional maintenance.
PW | 51 |  | Project | Greenleaf Sewer Rehabilitation | Sanitary sewer repair and lining for Greenleaf sewer in Chesterfield Gardens. |  | 167000 | 0 | 0 | 0 | 0 | 0 | Project will result in a reduction in the amount of calls for service for sewer cleaning to the Chesterfield Gardens. Previous costs: $21,436 Engineering Design
PW | 2 |  | Project | Implementation of Entrance and Roadway Signage Plan | In 2016, a comprehensive plan was developed for the installation of signage throughout the Village, including entrance signage and roadway signage identifying Niles and wayfinding to key points within Niles. |  | 404000 | 0 | 0 | 0 | 0 | 0 | This is a multi-year project with varying costs each year, dependent on signage constructed. These costs will be determined by which construction projects are scheduled for each location.
PW | 23 |  | Project | Lawrencewood Gardens and Oasis Neighborhood Storm Sewer Improvement | Storm sewer improvement from Mulford and Octavia to Howard Street Storm sewer outfall. |  | 0 | 0 | 0 | 0 | 0 | 10400000 | Project will likely result in a reduction in the amount of calls for service received from the Lawerencewood Gardens and Oasis Neighborhood. There is a potential for SSA funding.
PW | 18 |  | Project | Lead Service Line Replacement | Complete replacement of lead services lines which require emergency repair. |  | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | The annual cost to our water fund depends on how many repairs are required each year.
PW | 52 |  | Project | Melvina Street Rehabilitation | Pavement Rehabilitation Project from Touhy to Gross Point including watermain replacement, lighting, and bike improvements. |  | 0 | 2600000 | 0 | 0 | 0 | 0 | This is a TIF funded project. Previous costs: $297,810 Engineering Design
PW | 14 |  | Project | Milwaukee Avenue Crossing (Jonquil/Monroe) | Pedestrian safety crossings at the intersection of Milwaukee Avenue with Jon Quil Terrace and Monroe Street $1,600,000 Estimated construction and construction engineering cost $294,000 Estimated design engineering cost |  | 135000 | 150000 | 300000 | 0 | 0 | 0 | Previous funding: $4,500 for Warrant Study FY 22 Phs1 budgeted $135,000 (Not awarded due to scope questions) FY23 or FY 24 Phs 2 Engineering $150,000 FY25 or later Budget impact: $300,000 construction local match Schedule is dependent on IDOT and grant funding
PW | 30 |  | Project | Milwaukee Avenue Streetscape Phase V | Streetscape Improvements from Monroe to Greenwood |  | 4500000 | 0 | 0 | 0 | 0 | 0 | The project is grant dependent. Funding ratio is 80% federal and 20% local. There will be added maintenance costs for landscape brick pavers, street furniture, pedestrian lights, and irrigation systems.
PW | 31 |  | Project | Milwaukee Avenue Streetscape Phase VII | Streetscape Improvements at Milwaukee and Waukegan, as well as Oakton and Waukegan |  | 1250000 | 0 | 0 | 0 | 0 | 0 | The project is grant dependent. Funding ratio is 80% federal and 20% local. There will be added maintenance costs for landscape brick pavers, street furniture, pedestrian lights, and irrigation systems.
PD | 5 |  | Project | Niles Law Enforcement Memorial | The statue titled “The Protector” will feature a police officer standing atop a pedestal, saluting. An officer’s salute exhibits a long standing gesture of friendship, confidence and professionalism which is intended to honor all police officers killed in the line of duty, especially Niles Police Officer Steven Zourkas who was killed in the line of duty in 2005. |  | 35000 | 0 | 0 | 0 | 0 | 0 | Total project cost: $95,000.00. Public Works will be covering demolition, excavation and hauling of debris, electrical work, site utilities landscaping and some concrete work, which will cost approximately $20,000.00-$35,000.00. Anything beyond $35,000.00, will be paid for through donations by the Niles Law Enforcement Memorial Committee.
PW | 10 |  | Project | North Branch Trail Connection - Bunker Hill | Trail Connection from the intersection of Touhy and Caldwell to the North Branch Trail. |  | 580000 | 0 | 0 | 0 | 0 | 0 | Project is programmed for CMAQ (Congestion Mitigation and Air Quality Improvement) ($375,000) and Invest in Cook Funding ($112,500). Niles will spend $112,500 in local match.
PW | 12 |  | Project | Oakton Street and Caldwell Avenue - Multimodal improvements | Off-street pedestrian and multimodal improvements on Caldwell Avenue (FAU 0376) & Oakton Street (FAU 1332). From Vapor Lane to I-94 Edens Expressway. Morton Grove is leading this project and Niles is only responsible for cost sharing. Niles share is estimated at $260,000 total |  | 220000 | 0 | 0 | 0 | 0 | 0 | Previous funding: $40,000 for Phs 1 engineering cost share FY23 $220,000 FY24TBD Schedule is dependent on IDOT
PW | 11 |  | Project | Oakton Street Pedestrian network connections | Pedestrian network connections from the Chesterfield Gardens neighborhood to the newly improved pedestrian intersection of Caldwell and Oakton |  | 30000 | 170000 | 0 | 0 | 0 | 0 | FY23: $30,000 Design Engineering FY24: $170,000 Construction
PW | 24 |  | Project | Oketo Avenue Stormwater Improvement | Oketo Avenue Storm sewer replacement from Monroe Street to Keeney Street. |  | 0 | 650000 | 0 | 0 | 0 | 0 | Project will likely result in a reduction in the amount of calls for service on Oketo Avenue. This is a grant dependent project
PW | 25 |  | Project | Pavement Rehabilitation Senior Center (many times delayed - seven years) | Rehabilitation of the Senior Center Parking Lot |  | 200000 | 0 | 0 | 0 | 0 | 0 | The lot should be resurfaced on an approximately 15 year schedule.
PW | 15 |  | Project | Pedestrian Safety Improvements at Caldwell and Cleveland; Wauekgan and Cleveland | The Village is in the process of designing pedestrian crossing improvements at the above intersections. $85,487 Engineering Expenditure to date; $250,000 Estimated cost for final design and construction engineering; $1,900,000 estimate for construction |  | 1000000 | 1000000 | 0 | 0 | 0 | 0 | Previous funding: $85,487 for design FY 23 budget: $750,000-$1,500,000 Schedule is dependent on IDOT review. Federal funding eligible but that increases the project timeline 3-4 years.
PD | 3 |  | Project | Police Training Room Update | Update IT equipment including: replacing existing control tower with modern control function, create "one touch" system, create wireless Bluetooth connection, create wireless microphone system to be used by instructors and presenters, capability of displaying different outputs (linking with VON cameras i.e. LPR's surveillance cameras, etc.). Lastly, replacing stained carpet and adding electrical outlets to the floor. |  | tbd | tbd | tbd | tbd | tbd | tbd | 0
PW | 7 |  | Project | Public Works Salt Dome & Storage Facility (Phase 2 & 3) | Reconstruction of the public works salt dome and storage facility. |  | 190000 | 2000000 | 1700000 | 0 | 0 | 0 | There will be a reduction is salt purchasing cost as staff will not need to purchase salt during peak times. Overtime will be reduced for salt deliveries. Reduction in temporary repair costs associated with failing building and salt dome.
PD | 4 |  | Project | Records Configuration - Going Paperless | Reconfiguring the Police Records Department to improve the work space design and digitization of the paper records. |  | 70000 | 0 | 0 | 0 | 0 | 0 | Phase 1: Shelving - approximately $2,100 Phase 1: Cages - approximately $5,300 Phase 2: Digitization - approximately $60,000
PW | 17 |  | Project | Shermer Road - Rehabilitation and Multimodal Improvements | Rehabilitation of Shermer Road from Waukegan north to Village Limit. Project includes on-street bike and improvements per 2014 Bike and Ped plan. |  | 180000 | 180000 | 0 | 360000 | 360000 | 0 | FY23: $180,000 Phs 1 engineering FY24: $180,000 Phs 2 engineering FY26-27: $360,000 Local match
PW | 16 |  | Project | Touhy Avenue at Gross Point Road Intersection Improvements | Intersection improvement at Touhy and Gross Point Road. The improvement include a multimodal trail, roadway widening, left turn lanes, and lighting. Construction Cost estimate: $3,400,000 |  | 500000 | 0 | 0 | 0 | 0 | 0 | FY23 $160,000 Local Match FY23 $340,000 Phs 3 engineering (80% reimbursable) Previous expenditure: (LA Services $178,519; Phs 2 Design $223,813; Land Acquisition $1,045,000, Phs 1 Engineering $111,152)
PW | 29 |  | Project | Touhy Avenue Banner sign and monuments | Niles branded sign across Touhy Avenue at the Chicago River. Decorative Monument lights at Touhy Avenue Bridge. |  | 0 | 300000 | 0 | 0 | 0 | 0
PW | 26 |  | Project | Touhy Avenue Gap Lighting Franks Ave to Milwaukee Ave. (combine with proj 16) | The Gross Point and Touhy Intersection improvement includes new lighting up to the Chicago River Bridge. This project provides lighting for the gap between Franks and Milwaukee. |  | 160000 | 0 | 0 | 0 | 0 | 0 | There will be a minor increase to electricity costs. Cost is for design and construction.
PW | 82 |  | Project | Touhy Avenue Watermain Replacement | Touhy Avenue watermain replacement from Caldwell to Lehigh |  | 200000 | 3800000 | 0 | 0 | 0 | 0 | Watermain replacement reduces operational cost related to water loss and emergency watermain break repair.
PW | 20 |  | Project | Touhy Bridge Project - Local Improvements | The Village is responsible for various non-participating costs related to the Touhy Bridge project. |  | 0 | 650000 | 0 | 0 | 0 | 0
PW | 1 |  | Project | USACE Funded Stormwater Project | The Stormwater Commission will meet on 12/13/21 to select a project to receive USACE (Army Corps of Engineers) funding. |  | 331250 | 0 | 0 | 0 | 0 | 0 | Project will likely result in a reduction in the amount of stormwater-related calls for service received.
PW | 32 |  | Project | Village Hall Campus Redesign | The failing infrastructure, outdated aesthetics and lack of civic building pride is in need of a complete face-lift. |  | 250000 | 2750000 | 0 | 0 | 0 | 0 | The project is currently being planned. The FY23 component of the spending represents design, with construction planned in FY24.
PW | 88 |  | Project | Village Hall Interior Lobby Redesign | 0 |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0
PW | 83 |  | Project | Watermain Replacement Program FY24 - FY27 | Watermain replacement for end of service life watermains |  | 0 | 2000000 | 2000000 | 2000000 | 2000000 | 0 | Watermain replacement reduces operational cost related to water loss and emergency watermain break repair. Annual expenditure should be based on the ability to pay for the work as determined as a result of a rate study.
FD | 40 |  | Maintenance | Concrete Driveway Repair | The existing concrete driveway at Fire Station 2 is failing where the fire apparatus regularly drive through. This includes the front entrance to the fire station. |  | tbd | tbd | tbd | tbd | tbd | tbd | 0
PW | 41 |  | Maintenance | Crack Sealing | Annual crack sealing of roads to prevent water infiltration. |  | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | Reduction in damage to roadways. With proper maintenance the roads will be safer for pedestrians and vehicular traffic. Life of roads will be extended lessoning the cost of street replacement.
PW | 86 |  | Maintenance | Employee Parking Lot Gate and Man-Door Replacement | Replace existing swing gate and man-door with a secure, motorized system similar to the Touhy Ave. and Franks Ave. access gates. |  | 75000 | 0 | 0 | 0 | 0 | 0 | Minimal, but aesthetic and security considerations are important.
PW | 39 |  | Maintenance | Fire hydrant flushing and testing program | Flush and test all Village fire hydrants. |  | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | Provides necessary information of the Village’s water distribution system and increases the safety of the residents and businesses in Niles.
FC | 37 |  | Maintenance | Fitness Center HVAC Gym Roof Top Units (RTU) | Replacement of two existing Gym HVAC RTUs. |  | 0 | 120000 | 0 | 0 | 0 | 0 | These are the last two original HVAC units to be replaced. They are currently over 20 years old and have met their life expectancy. Currently, the fitness center has no backup Gym HVAC RTU's that can be used during extreme weather conditions where temperatures fluctuate or in the case of RTU failure. The gymnasium is a multi-use fitness area that requires quality air circulation and temperature control.
PW | 63 |  | Maintenance | Full roof restoration at 7000 W. Touhy | Repair Adverse Membrane Conditions Present. Removal of Areas of Wet Insulation. Installation of New Perimeter and Penetration Flashings. Thorough Cleaning of Existing Membrane Surfaces. Application of New Restoration Treatment at Rates Specified. Application of New Surfacing Option |  | 310000 | 0 | 0 | 0 | 0 | 0
PW | 87 |  | Maintenance | HVAC Replacements (IT Room) at 1000 Civic Center Drive. | Replace Liebert units in server room with modern equipment designed to handle additional IT infrastructure. |  | 80000 | 0 | 0 | 0 | 0 | 0 | The project will likely prevent or reduce further emergency maintenance or repairs, likely coming from the General Fund.
PW | 59 |  | Maintenance | HVAC Replacements at 7000 W. Touhy | Rooftop Unit RTU-1 serving Jail Cells,Rooftop Unit RTU-3 serving Lower Level Locker Rooms,Rooftop Unit, Rooftop Unit RTU-6 serving the Second Floor Offices, Add Mini-Split System to Fingerprint Area,Computer Room Unit CRIU-3 ducted cooling unit and remote condenser serving Lower Level Electrical Room |  | 300000 | 0 | 0 | 0 | 0 | 0
PW | 58 |  | Maintenance | HVAC Replacements at PW Campus | Replacements of Above ceiling Computer Room Unit remote condenser serving Server Rooms |  | 50000 | 0 | 0 | 0 | 0 | 0
PW | 60 |  | Maintenance | HVAC Replacements Shared Units for Senior Center and Family Services | Hot Water Pumps serving entire building AHU-1 serving Senior Center & Family Services AHU-1 Variable Frequency Drives serving Senior Center & Family Services Wood gas piping supports on roof are deteriorated. Trane Temperature Controls serving building are obsolete |  | 725000 | 0 | 0 | 0 | 0 | 0
PW | 55 |  | Maintenance | Lower Level Mechanical Roof, Chiller and Access Door | Replacement of the Lower Level Mechanical Roof, Chiller Unit and Access Door at Village Hall |  | 270000 | 0 | 0 | 0 | 0 | 0
FC | 38 |  | Maintenance | Membership Service Desk (Front Desk)-Remodel | The Membership Service Desk (Front Desk) will be remodeled. |  | 0 | 9700 | 0 | 0 | 0 | 0 | This project will not be revenue producing and expenses are minor. The project will improve building aesthetics and potentially offer minor improvements to operations involving customers interacting with staff behind the counter.
PW | 53 |  | Maintenance | Milwaukee Brick Crosswalk Replacement | Replacement of Decorative Milwaukee Crosswalks with Thermoplastic Crosswalks |  | 250000 | 25000 | 250000 | 25000 | 250000 | 0 | The cross walks will need to be replaced every 10-years or so. Replacement costs will be much less than the initial cost since much of the initial cost is related to removal of the brick paver walk.
PW | 44 |  | Maintenance | Minor Asphalt Repairs | Repairs of large section of roadways. |  | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | With proper maintenance the roads will be safer for pedestrians and vehicular traffic. Life of roads will be extended and delay street replacement. Reduction in overtime for filling potholes. Reduction in injuries to pedestrians from stepping in cracked and broken roadways.
PW | 42 |  | Maintenance | Pump Replacement: #2 and Pump # 4; add VFD's. | Replacement of pump #2 and installation of a new VFD on pump #4 at the Touhy Avenue Pump Station. |  | 234000 | 0 | 0 | 0 | 0 | 0 | The previous funding for replacement of motors and pumps and installing VFD's was $180,000. Staff is anticipating a thirty-percent increase for materials.
PW | 61 |  | Maintenance | Repair/Replacement of Exterior Walls,Gutters and Soffits at 999 Civic Center Drive | An exterior refresh of 999 Civic Center Drive is needed to assure the building envelope health. Tuckpointing, and cleaning of the brickwork is required in various areas of the building, the gutters and downspouts are in need of replacement, along with the water damaged soffit overhang in the rear of the building. |  | 250000 | 0 | 0 | 0 | 0 | 0
PW | 56 |  | Maintenance | Replacement of Exterior Door and Frames at 1000 Civic Center Drive | Demolition and replacement of 12 exterior doors and framework 1000 Civic Center Drive |  | 108000 | 0 | 0 | 0 | 0 | 0
PW | 65 |  | Maintenance | Replacement of Exterior Door and Frames at PD Campus | Demolition and replacement of 5 exterior doors and framework of the PD Campus |  | 45000 | 0 | 0 | 0 | 0 | 0
PW | 66 |  | Maintenance | Replacement of Exterior Door and Frames at PW Campus | Demolition and replacement of 21 exterior doors and framework of the PW Campus |  | 170000 | 0 | 0 | 0 | 0 | 0
FC | 35 |  | Maintenance | Replacement of Flooring in Cardio/Weight Area of the Fitness Center | The carpet and mondo flooring in Cardio/Weight Area of the Fitness Center will be replaced. The type of flooring replacement and configuration will be determined by the vendor's evaluation/quoted fee. |  | 0 | 56550 | 0 | 0 | 0 | 0 | Replacement and reconfiguration of the carpet/mondo flooring will allow for expansion of the weight area. This is a request from not only our current membership base but the future of fitness workout. We believe this re-configuration of the fitness room will attract a younger membership base. While we acknowledge increasing the weight area will decrease the cardio area, this will allow fitness staff to evaluate the use of cardio equipment, such as not repairing equipment (expense) that is end of life and not being used by members (waste of floor space).
FC | 34 |  | Maintenance | Replacement of Front Lobby Doors Interior and Exterior | The Front Lobby doors of the Fitness Center, both interior and exterior, will be replaced. The type of replacement will be determined by evaluation/quoted fee from vendor. |  | 0 | 50000 | 0 | 0 | 0 | 0 | The Front Lobby Doors will be under warranty for a period of time. The number of service calls to vendors and to PW for assistance will be reduced. IT will ensure that replacement doors work with existing fitness center security systems, including the scheduling of opening/closing the building entrances/exits.
FC | 36 |  | Maintenance | Re-Support of Pool Duct Work To Beams | Labor, materials, and scaffold are required to install additional trapeze for all duct work hanging over pool area. |  | 21980 | 0 | 0 | 0 | 0 | 0 | One time expense for continued operations and safety.
PW | 48 |  | Maintenance | Sewer Cleaning and Televising Program | The sewer cleaning and televising program is to clean debris from both sanitary and storm lines and find structural deficiencies. |  | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | Identify the scope of the repairs necessary, including sewer lining, spot repairs or complete pipe section excavation and replacement.
PW | 49 |  | Maintenance | Sewer Lining Program | CIPP is designed to restore our sewer lines to proper operating conditions. |  | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | CIPP sewer lines that are deteriorating.
PW | 45 |  | Maintenance | Traffic Signal Maintenance | Traffic signal maintenance of intersection in the Village of Niles. |  | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 53788.56 | 53788.56
PW | 43 |  | Maintenance | Tree Planting | Planting trees along village parkways and properties. |  | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | Trees require maintenance. In order to invest in the growth of Niles and its green infrastructure, Niles will need to commit funding to maintain village trees.
PW | 47 |  | Maintenance | Tree Removal | Tree Removal along village owned parkways and properties. |  | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | Removal of these trees reduces call outs for storm damage, hangers, damage to property and most of all reduces the danger to life. Insurance claims are lower and phone calls to the department for service are reduced.
PW | 46 |  | Maintenance | Tree Trimming | Tree Trimming along village owned parkways and properties. |  | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | Trees require maintenance and trimming reducing call outs for storm damage, hangers, damage to property and most of all reduces the danger to life.
PW | 62 |  | Maintenance | Truck Wash Restoration | Reconfigure and plumb undercarriage wash, repair drainage, and reseal repaired concrete. |  | 90000 | 0 | 0 | 0 | 0 | 0
PW | 50 |  | Maintenance | Water main Valve Exercising Program | To ensure that water valves can be located efficiently and closed to isolate part of the water system in case of an emergency, water main breaks or repair. |  | 82000 | 82000 | 82000 | 82000 | 82000 | 82000 | Repair inoperable valves when found to ensure the water system is working properly.
PW | 79 |  | IT/Purchase | 499 Street Sweeper Replacement | Replacement unit will serve as the primary street sweeper for sweeping and leaf-pickup operations. |  | 300000 | 0 | 0 | 0 | 0 | 0
IT | 67 |  | IT/Purchase | Audio Visual and Conference Room Improvements | A/V and conferencing systems update/refresh. |  | 28000 | 0 | 0 | 0 | 0 | 0 | Many of our current A/V and conferencing systems at the Village Hall (Council Chambers, 1st and 2nd Floor conference rooms), Police Station (training room), Fitness Center, and Family Services (Multi-Purpose rooms) must be refreshed as they have gone past their useful life.
IT | 80 |  | IT/Purchase | End-User Device Refresh - CD | Refresh Community Development Department End-User Devices for Inspectors, and Managers. |  | 28000 | 500 | 500 | 500 | 500 | 500
IT | 68 |  | IT/Purchase | End-User Device Refresh Lifecycle | Refresh end-user desktops at the end of life 4~5 year cycle at the rate of 50 desktops a year. -This will include desktop or laptop and typical peripherals such as scanners, webcams, headsets, monitors, docking stations, software licenses, including end-point protection, i.e., antivirus and malware protection. |  | 70000 | 0 | 0 | 0 | 0 | 0 | The village needs to be on a regular end-user device refresh life cycle to maintain its fleet of computers functional and in operating conditions.
PW | 84 |  | IT/Purchase | Holiday Decorations | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT | 69 |  | IT/Purchase | IT Infrastructure Improvements | Network and Wifi remedation |  | 98000 | 0 | 0 | 0 | 0 | 0 | The Village's IT Network and WiFi infrastructure have been plagued with network outages that have crippled the staff's ability to utilize the IT network and Internet Services. Network remediation will address network availability and reliability.
IT | 70 |  | IT/Purchase | O365/M365 Migration | Office 365 migration |  | 92600 | 0 | 0 | 0 | 0 | 0 | Currently, the Village hosts many Microsoft Enterprise services on-premises that have been less and less reliable and require a more advanced skill set to administer, manage, and current. The on-premises model has become unsustainable and is plagued with system outages.
FD | 72 |  | IT/Purchase | Purchase New Ambulance | Replace heavily used and worn out ambulance from 2009. A new ambulance will allow for a reliable vehicle to respond to medical emergencies without delay. |  | 0 | 325000 | 0 | 0 | 0 | 0
FD | 73 |  | IT/Purchase | Purchase New Fire Engine | Replacement of aging and deteriorating 1992 fire engine. |  | 0 | 875000 | 0 | 0 | 0 | 0
PW | 74 |  | IT/Purchase | Replace (11) Civic Center Vehicles with (8) Electric "Motor Pool" Vehicles | Replace (11) General Government Vehicles, (10) 2007 Ford Fusions and (1) 2000 Crown Victoria with (8) Electric "Motor Pool" Vehicles. This project will also include charges that will be installed by the Village Electrician. |  | 0 | 400000 | 0 | 0 | 0 | 0
PW | 75 |  | IT/Purchase | Replace (2) Detective Sedans Units #104 and #107 | Replace (2) 2007 Dodge Charger Sedans with (2) 2023 Police SUV's |  | 90000 | 0 | 0 | 0 | 0 | 0
PW | 76 |  | IT/Purchase | Replace (2) Water Department Trucks Units #440 and #472 | Replace (2) Water Department trucks 2008 and 2006 models with (2) 2023 Utility Body trucks. The replacement vehicles will be built on Ford F-350 Chassis and Knapheide service bodies that will be used by the water department for service calls and for winter snow removal operations. |  | 170000 | 0 | 0 | 0 | 0 | 0
PW | 78 |  | IT/Purchase | Replace Sewer Department Van #478 | Replacement of Water Department Cube Van #478 2008 Chevrolet E3500 Upfit with Morgan Olsen Route Star Walk-In Van body and applicable hardware for water main repairs. |  | 180000 | 0 | 0 | 0 | 0 | 0
IT | 71 |  | IT/Purchase | SCADA Security | Secure the Village's Supervisory control and data acquisition (SCADA) system. SCADA is a system of software and hardware elements that enables the Water Department to control industrial processes locally or at remote locations; Monitor, gather, and process real-time data; Directly interact with devices such as sensors, valves, pumps, motors, and more through human-machine interface (HMI) software; Record events into a log file; |  | 36000 | 0 | 0 | 0 | 0 | 0 | Securing the Village's critical infrastructure Water Supply Plant from cyberattacks by minimizing vulnerabilities. Additional capabilities include capacity to monitor, gather, and process real-time data; directly interact with devices such as sensors, valves, pumps, motors, and more through human-machine interface (HMI) software; record events into a log file.
0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0

## Removed Items
Dept. ID | Project # | SP Area | SP Area Secondary Category | CIP Category | Project Title | Description | Justification | Impact | Fund Impact | Priority Tier | Elected Priority | Project Rank | Sunk Cost | Cost Total | FY23 | FY 24 | FY 25 | FY 26 | FY 27 | FY 28 | GF FY23 | General Fund | Fitness | Capital Fund | MFT | TIF | Water Fund | Auto Fund | Cash | Loan | Bond | Grants | Funding Total | SP Area
PW | 54 | Infrastructure Planning and Funding | Blank | Project | Village Hall Parking Garage Security and Thermal Intrusion Upgrade | Replace the chain roll up garage doors and man door with solid aluminum doors. Add removable thermal glass panes over the steel mesh steel windows, and piping insulation; potential inclusion with Village Hall Entrance Reconstruction | Replacing the mesh roll up garage doors and adding thermal glass panes to the underground parking garage will reduce cold/hot weather intrusion, increase security, eliminate bird traffic, and improve the garage aesthetic my increasing cleanliness. | Reducing thermal intrusion and lowering carbon footprint by reducing HVAC necessity |  | 2 |  |  |  | 150000 | 150000 | [5 empty] | 150000 | 150000 | [10 empty] | 150000
PW | 64 | Infrastructure Planning and Funding | Foster Community Identity | Maintenance | Restoration vestibule stairs, walkway and guardrail at 7000 W. Touhy | Remove damaged pre-cast concrete from stairs and walkway, replace damaged metal frame work and guardrail, replace cement, paint and seal finished components. | The vestibule walkway, stairs and guardrail is badly corroded from winter conditions and needs restoration before complete system failure occurs | A restoration of an existing vestibule stairway is a lower cost alternate to full replacement |  | 2 |  |  |  | 200000 | 200000 | [5 empty] | 200000 | 200000 | [10 empty] | 200000
PW | 57 | Infrastructure Planning and Funding | Blank | Maintenance | HVAC Replacements at 1000 Civic Center Drive. | Replace Liebert units in server room and server room ceiling with modern equipment that is designed to handle additional IT infrastructure. | The aforementioned HVAC units have surpassed their life expectancy or are entirely obsolete and require replacement. | Being that the project is multi-tiered, workload permitting, Facilities staff can be utilized to reduce costs by purchasing individual units and installing in-house |  | 2 |  |  |  | 80000 | 80000 | [5 empty] | 80000 | 80000 | [10 empty] | 80000
Note on A1: Department Abbreviations: Department: PW - Public Works PD - Police FD - Fire FC - Fitness Center SC - Senior Center FS - Family Services CD - Community Development FIN - Finance IT - Information Technology AD - Administration
Note on C1: STRATEGIC PRIORITY AREA: This is define in the Strategic Planning document and consists of one or more of the following: 1) Financial Stability and Transparency; 2) Diversified Economic Development; 3) Marketing and Communication; 4) Infrastructure Planning and Funding; 5) Foster Community Identity.
Note on K1: Schultz, Conor: Tier 1: Must-Have projects to be completed for stability of services Tier 2: Resources (financing and capacity) are available for the designated budget year Tier 3: Stretch goal/Resources Unavailable/Further Clarification Required
Note on M1: Overall Institution Rank.
Note on F2: Schultz, Conor: tieto VillageHall Entrance
Note on C4: Schultz, Conor: This item was accidentally duplicated prior to numbering and is now removed